# Sprint Retrospective Meeting Minutes

Sprint Retrospective Meeting Minutes

Project: Canvas AI Assistant

Attendees: Nitin Chokkalla, Edgar Velarde, Alberto Abrahantes, Sebastian Rodriguez, Jin Carballosa

Start time: 8:00pm

End time: 9:10pm

What went wrong?

- Did we do a good job estimating our team’s velocity?

 ○ Partially. While research-heavy stories were completed, implementation stories (Canvas API sync, DB schema) were underestimated. Velocity was overestimated in terms of deliverables.

- Did we do a good job estimating the points (time required) for each user story?

 ○ No. Stories involving technical setup (API integration, database) took longer than planned. Research stories were easier to estimate, but implementation scope was underestimated.

- Did each team member work as scheduled?

 ○ Yes. Everyone committed time consistently, but workload distribution wasn’t even across all stories. Some members were blocked while others still had availability.

What went right?

- We successfully gathered framework knowledge (Flask vs FastAPI), Canvas API documentation insights, and wireframe refinements.

- The team collaborated daily, with everyone sharing updates and challenges openly.

- A solid foundation was set for the backend architecture and client integration testing.

How to address the issues in the next sprint?

- How to improve the process?

 ○ Better sprint planning is needed to balance research vs implementation stories. Tasks should be divided so all members stay fully engaged without bottlenecks.

 ○ Dependencies (e.g., needing database schema before API coding) should be flagged earlier so parallel work can happen.

- How to improve the product?

 ○ Shift focus from research into coding deliverables (API endpoints, DB schema setup, GitHub repo commits).

 ○ Begin with Canvas API integration and a minimal working backend, even if features are limited, so we can iterate on actual functionality instead of just planning.

# Tab 2

Sprint Retrospective Meeting Minutes

Project: Canvas AI Assistant

Attendees: Nitin Chokkalla, Edgar Velarde, Alberto Abrahantes, Sebastian Rodriguez, Jin Carballosa

Start time: 8:00pm

End time: 9:10pm

What went wrong?

- Did we do a good job estimating our team’s velocity?

 ○ Not fully. We improved compared to the last sprint, but syncing tasks (retry logic, batching, pagination) required more cycles than anticipated. Velocity was again slightly overestimated.

- Did we do a good job estimating the points (time required) for each user story?

 ○ No. Backend integration stories were consistently underestimated. Test automation stories were closer to accurate but still underestimated due to schema updates mid-sprint.

- Did each team member work as scheduled?

 ○ Yes. Everyone put in consistent effort, but some members were blocked by backend instability while others could proceed with UI-related tasks.

What went right?

- Backend endpoints for assignments and announcements were implemented and tested against Canvas with real payloads.

- Test automation improved significantly, with broader coverage across endpoints and regression cases.

- UI integration began to reflect live backend data, with error handling flows working end-to-end.

- Team collaboration remained strong, with frequent pairing to unblock issues and validate fixes.

How to address the issues in the next sprint?

- How to improve the process?

  - Break large technical stories (e.g., sync batching + pagination) into smaller, independently testable tasks.

  - Proactively surface risks during sprint planning so dependencies can be tackled earlier.

  - Use mid-sprint checkpoints to reassess velocity and adjust workload before bottlenecks pile up.

- How to improve the product?

  - Prioritize stabilizing backend sync logic to reduce ripple effects on testing and UI work

  - Expand CI pipeline to include automated regression tests, ensuring changes don’t repeatedly break existing flows.

  - Deliver a minimal end-to-end demo (UI + backend + Canvas data) to confirm integration is functional before polishing features.

# 10/26/2025

Sprint Retrospective Meeting Minutes

Project: Canvas AI Assistant

Attendees: Nitin Chokkalla, Edgar Velarde, Alberto Abrahantes, Sebastian Rodriguez, Jin Carballosa

Start time: 8:00pm

End time: 9:10pm

What went wrong?

- Did we do a good job estimating our team’s velocity?

 ○ Partially. Our estimates were more consistent than before, but some cross-team dependencies (such as sync and retry flows) required more rework than planned. Velocity continues to trend upward but still needs calibration

- Did we do a good job estimating the points (time required) for each user story?

 ○ Not entirely. Backend and integration stories were again underestimated, mainly due to unexpected data-schema changes and additional debugging effort. Test automation estimates improved but still carried some hidden setup costs.

- Did each team member work as scheduled?

 ○ Yes. The team maintained steady effort throughout the sprint, though some progress was slowed by environment instability and delayed API responses from Canvas.

What went right?

- Backend sync for assignments and announcements continued to stabilize, successfully processing real Canvas payloads.

- Automated testing expanded, providing higher regression coverage and early detection of integration issues.

- The UI now reflects real-time backend data, with pagination and error handling functioning end-to-end.

- Communication and teamwork remained strong, with effective pairing and quick responses to blockers.

How to address the issues in the next sprint?

- How to improve the process?

  - Further decompose complex sync stories into smaller, verifiable subtasks to improve visibility and testing.

  - Continue mid-sprint velocity check-ins to recalibrate scope before bottlenecks arise.

  - Identify technical risks earlier in sprint planning to allocate buffer time for unexpected backend changes.

- How to improve the product?

  - Expand the CI/CD pipeline with nightly automated regression tests.

  - Focus on optimizing backend reliability and reducing sync retries to minimize cascading delays.

  - Prepare a fully functional end-to-end demo (UI + backend + Canvas data) early in the sprint to validate integration before refinement work.

# Tab 4

Sprint Retrospective Meeting Minutes

Project: Canvas AI Assistant

Attendees: Nitin Chokkalla, Edgar Velarde, Alberto Abrahantes, Sebastian Rodriguez, Jin Carballosa

Start time: 8:00pm

End time: 9:10pm

What went wrong?

- Did we do a good job estimating our team’s velocity?

◦ Partially. Although several user stories were completed, integration points—especially around the CI pipeline, schema updates, and sync batching—introduced more delays than anticipated. These extra debugging cycles slightly reduced the team’s overall velocity.

- Did we do a good job estimating the points (time required) for each user story?

◦ Not fully. Continuous Integration setup and schema finalization demanded more configuration and verification than originally estimated. The tasks that weren’t completed—error logging dashboard, preference sync, and regression test suite—were delayed mostly due to missing API keys, inconsistent client-to-backend data propagation, and pending CI pipeline integration. These blockers were not fully accounted for in the initial estimates.

- Did each team member work as scheduled?

 ◦ Yes. Team members worked consistently across backend, frontend, and testing activities. Most delays were due to external dependencies (e.g., CI alerting integration, migration setup, waiting on API access), not lack of collaboration or effort. Handoffs were smooth, but blocked tasks impacted pacing.

What went right?

- Sync batching & pagination (User Story #10) worked reliably during large dataset transfers, significantly improving performance.

- CI/CD pipeline (User Story #11) was successfully implemented with automated build, test, and deployment workflows triggered on main-branch merges.

- Database schema finalization (User Story #12) improved consistency, reduced data ambiguity, and simplified backend interaction with the Canvas API.

- Collaboration across modules was strong—backend, API, and testing integration showed minimal merge issues.

- The completed stories demonstrated clear functional progress across the system, especially around scalability and infrastructure.

How to address the issues in the next sprint?

- How to improve the process?
◦ Account for integration dependencies when estimating stories.
 Unexpected setup steps for CI and schema migrations should be added into story point calculations.

- ◦ Add mid-sprint review checkpoints.
 Blocked items like missing API keys or incomplete CI integration can be caught early to prevent rollover at sprint end.

- ◦ Improve documentation around setup steps.
 CI/CD configuration, migration steps, and required API integrations should be documented to reduce confusion and configuration delays.

- How to improve the product?
◦ Complete integration for delayed user stories.
 Finish linking the Error Logging Dashboard to the CI alerting system, complete preference sync consistency fixes, and finalize regression test automation.

- ◦ Optimize sync and pagination performance further.
 Now that batching works, add indexing, caching, or tuning to improve large dataset throughput.

- ◦ Expand automated testing.
 Integrate schema validation tests and regression workflows into the CI pipeline to reduce future deployment friction.