# Loan Validation — Backlog Grooming Meeting Minutes

Date: Monday, November 3, 2025

Time: 1 hour

Attendees: Ernesto, Carlos, Luis, Chris, Miguel

## 1) Purpose

Refine and prioritize the product backlog so it aligns with our sprint cadence and near‑term demo goals. Confirm scope, acceptance criteria, estimates, dependencies, and ownership for upcoming work.

## 2) Sprint Timeline Alignment

Sprint 1: Sep 1 – Sep 14, 2025 (Foundations, initial OCR POC, repo setup)

Sprint 2: Sep 15 – Sep 28, 2025 (Secure storage, IRS API via MCP stub, initial QA checklist)

Sprint 3: Sep 29 – Oct 12, 2025 (Data integration, logging, technical architecture flowchart)

Sprint 4: Oct 13 – Oct 26, 2025 (DMV API stub, orchestration logging improved, first fraud rule pass)

Sprint 5 (current): Oct 27 – Nov 9, 2025 (Dashboard MVP, expanded OCR validation, Trust Index calibration)

Sprint 6 (forecast): Nov 10 – Nov 23, 2025 (Live API hardening, cross‑doc validation rules v2, demo polish)

Today’s grooming goal: lock Sprint 5 remainder and stage Sprint 6 scope at a high level.

## 3) Backlog — Proposed Order (MoSCoW + Story Points)

Scale: S=1, M=3, L=5, XL=8, XXL=13

Must‑Have (Sprint 5 focus):

Dashboard MVP with 3 KPIs (Agent Confidence, Validation Risk, Trust Index overall)

OCR Validation on Expanded Dataset

Fraud Rule: Mismatched Tax ID ↔ Address (v2)

Retry/Backoff + Observability for IRS Stub

Ground‑Truth Table Generator (from scanned docs)

Should‑Have (end of Sprint 5 if capacity remains):

Validation Rules Engine v1 (config‑driven)

Trust Index Calibration v1

Could‑Have (seed for Sprint 6):

DMV Integration: from Stub → Live Sandbox

Document Parsing Schema v2 (multi‑doc, cross‑refs)

Security/PII Handling Checklist v1

Won’t‑Have (this iteration): Model retraining with external paid datasets — defer until post‑demo budget clarity.

## 4) Acceptance Criteria (consolidated)

Dashboards: Loads ≤3s on 10k‑row staging; export produces ≤5MB CSV; numbers match SQL aggregates ±0.5%.

OCR Validation: Report shows precision/recall per field; fails build if Name/Phone/Gross Pay F1 < 0.95.

Rules Engine: YAML → JSON IR → execution → findings table; 100% unit test coverage on parser.

Trust Index: Documented weights; unit tests per weight; displayed on dashboard as 0–100.

## 5) Dependencies & Risks

Data labeling pace may bottleneck OCR validation. Mitigation: assign 2nd labeler (Chris) and use consensus.

API instability on IRS/DMV. Mitigation: robust retry/backoff + feature flags.

Scope creep on dashboard visuals. Mitigation: freeze MVP to 3 KPIs + one drill‑through.

## 6) Estimates Review

Velocity reference (last 2 sprints average): ~20–22 pts.

Sprint 5 committed after grooming (Must‑Have total): 24 pts → stretch but acceptable; move item 5 to Should‑Have if needed.

## 7) Decisions

Keep DMV live move as Sprint 6 seed item (behind feature flag).

Trust Index shows overall + per‑document sub‑scores (hover tooltip), not per‑field (defer).

Findings schema to include severity, rule_id, doc_id, applicant_id, timestamp.

## 8) Action Items (owners & due dates)

Carlos/Chris: Dashboard MVP skeleton with static mocks → Nov 5.

Ernesto: Expand labeled dataset to 200 docs; publish GT generator v0.1 → Nov 6.

Luis: Rule mismatch TIN↔Address v2 with tests → Nov 6.

Miguel: IRS stub retry/backoff + observability → Nov 5.

## 9) Parking Lot

Per‑field Trust Index components (after demo).

Third‑party address normalization options (post‑budget).

## 10) Updated Backlog (Short List)

Dashboard MVP (5)

OCR Validation Expanded (8)

Fraud Rule v2 (3)

IRS Retry/Backoff + Obs (3)

GT Table Generator (5)

Rules Engine v1 (8)

Trust Index Calibration (3)

DMV Live Sandbox (8)

Parsing Schema v2 (5)

Security/PII Checklist (3)