## GanttChart
Course Evaluation System
Capstone 2: Gerardo Parra, Daniel Nunez, Shaoting Wu, Artur Vorojeykin, Mariela Torres Zuniga, Amani Hunt
| Project Start Date: |  | 2022-08-29 |  | Display Week: |  | 8 | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12 | [6 empty] | Week 13 | [6 empty] | Week 14 | [6 empty] | Week 15
| Project Owner: |  | Nagarajan Prabakar |  |  |  |  | 2022-10-17 | [6 empty] | 2022-10-24 | [6 empty] | 2022-10-31 | [6 empty] | 2022-11-07 | [6 empty] | 2022-11-14 | [6 empty] | 2022-11-21 | [6 empty] | 2022-11-28 | [6 empty] | 2022-12-05
 | time axis 2022-10-17 to 2022-12-11
WBS | Task | Lead | Start | End | Days | % Done | Work Days | time axis 2022-10-17 to 2022-12-11
1 | Sprint 1 | All Members | 2022-08-29 | 2022-09-11 | 14 |  | 10
1.1 | Focused on getting familiar with current CES applications. | All Members | 2022-08-29 | 2022-08-30 | 2 | 100% | 2
1.2 | Worked on formalizing project goals. | All Members | 2022-08-31 | 2022-09-01 | 2 | 100% | 2
1.3 | Worked on getting familiar with the technologies being used for the new version of CES. | All Members | 2022-09-02 | 2022-09-03 | 2 | 100% | 1
1.4 | Communicate with the product owner on the list of issues. | All Members | 2022-09-04 | 2022-09-05 | 2 | 100% | 1
1.5 | Started to design the new database in PostgreSQL | Gerardo | 2022-09-06 | 2022-09-07 | 2 | 100% | 2
1.6 | Created github repository | Gerardo | 2022-09-08 | 2022-09-09 | 2 | 100% | 2
1.7 | Created backend in Django | Gerardo | 2022-09-10 | 2022-09-11 | 2 | 100% | 0
2 | Sprint 2 |  | 2022-09-12 | 2022-09-25 | 14 |  | 10
2.1 | Created models for the database. | All Members | 2022-09-12 | 2022-09-15 | 4 | 100% | 4
2.2 | Created serializers to convert objects into data types. | All members | 2022-09-16 | 2022-09-20 | 5 | 100% | 3
2.3 | Created views to return a web response. | All members | 2022-09-21 | 2022-09-25 | 5 | 100% | 3
3 | Sprint 3 |  | 2022-09-26 | 2022-10-09 | 14 |  | 10
3.1 | Started creating scripts to add data to the database | Daniel, Jose | 2022-09-26 | 2022-09-29 | 4 | 100% | 4
3.2 | Created scripts in Bash and Python to show to PO and decided to use Python | Daniel, Jose | 2022-09-30 | 2022-10-03 | 4 | 100% | 2
3.3 | Started creating authentication to use token based authentication. | Jose | 2022-10-04 | 2022-10-07 | 4 | 100% | 4
3.4 | Started creating rest actions to retrieve and post information to the database. | Gerardo | 2022-10-08 | 2022-10-09 | 2 | 100% | 0
4 | Sprint 4 |  | 2022-10-10 | 2022-10-23 | 14 |  | 10
4.1 | Added some changes to the new database schema. | Shaoting, Artur, Daniel, Gerardo | 2022-10-10 | 2022-10-11 | 2 | 100% | 2
4.2 | Continued adding scripts to add data to the database. | Daniel | 2022-10-12 | 2022-10-13 | 2 | 100% | 2
4.3 | Finished creating token based authentication. | Jose | 2022-10-14 | 2022-10-15 | 2 | 100% | 1
4.4 | Continued creating more possible actions to use later. | All Members | 2022-10-16 | 2022-10-17 | 2 | 100% | 1
4.5 | Created a frontend in React. | Daniel | 2022-10-18 | 2022-10-19 | 2 | 100% | 2
4.6 | Created two pages: LoginPage and StudentPage. | Daniel, Gerardo | 2022-10-20 | 2022-10-23 | 4 | 100% | 2
5 | Sprint 5 |  | 2022-10-24 | 2022-11-06 | 14 |  | 10
5.1 | Created an evaluation page, so students are able to take the evaluations. | Daniel | 2022-10-24 | 2022-10-26 | 3 | 100% | 3
5.2 | Worked on frontend StudentPage and EvaluationPage | Daniel, Gerardo | 2022-10-27 | 2022-10-29 | 3 | 100% | 2
5.3 | Continued creating more scripts. | Jose | 2022-10-30 | 2022-11-01 | 3 | 100% | 2
5.4 | Continued creating more actions requested by frontend developers. | Shaoting, Artur | 2022-11-02 | 2022-11-04 | 3 | 100% | 3
5.5 | Started a LoginPage and FacultyPage for faculty users. | Daniel, Gerardo | 2022-11-05 | 2022-11-06 | 2 | 100% | 0
6 | Sprint 6 |  | 2022-11-07 | 2022-11-20 | 14 |  | 10
6.1 | Worked on finalizing faculty changes requested by PO. | Gerardo | 2022-11-07 | 2022-11-09 | 3 | 100% | 3
6.2 | Worked on cli, and made commands to add data interactively. | Jose | 2022-11-10 | 2022-11-12 | 3 | 100% | 2
6.3 | Worked on wrapping up the bugs. | All Members | 2022-11-13 | 2022-11-16 | 4 | 100% | 3
6.4 | Worked on finalizing student changes requested by PO. | Daniel | 2022-11-17 | 2022-11-20 | 4 | 100% | 2
7 | Sprint 7 |  | 2022-11-21 | 2022-12-04 | 14 |  | 10
7.1 | Worked on doing all the documentation of the whole system. | All members | 2022-11-21 | 2022-11-23 | 3 | 100% | 3
7.2 | Worked on doing video tutorials to show how to set up the system, and how it works. | Mariela, Shaoting, Jose | 2022-11-24 | 2022-11-26 | 3 | 100% | 2
7.3 | Worked on deploying the project into the server provided by Eric. | Gerardo | 2022-11-27 | 2022-11-30 | 4 | 100% | 3
7.4 | Worked on doing tests on the whole system. | Daniel | 2022-12-01 | 2022-12-04 | 4 | 100% | 2

## TermsOfUse
Terms of Use
Gantt Chart Template for Google Sheets
© 2012-2018 Vertex42 LLC. All rights reserved.
This template is a copyrighted work under the Unites States and other copyright laws and is the property of Vertex42 LLC. The items listed below are additional points to help clarify how you may use this template.
You may make archival copies and customize this template only for your personal use or use within your company or organization and not for resale or public sharing.
You may not remove or alter any logo, trademark, copyright, disclaimer, brand, terms of use, attribution, or other proprietary notices or marks within this template.
This template and any customized or modified version of this template may NOT be sold, distributed, published to an online gallery, hosted on a website, or placed on a public server.
The Share Settings for this spreadsheet must always be set to "Private"
Limited Private Sharing and Other Allowed Uses
See the complete license agreement to learn more about how you may or may not use this template.
View the Complete License Agreement
https://www.vertex42.com/licensing/EULA_privateuse.html

## © (hidden)
Gantt Chart Template
© 2012-2014 Vertex42 LLC
Please note the Terms Of Use
http://www.vertex42.com/licensing/EULA_privateuse.html