## Sheet1
pyTLEX Sprint 7 Backlog
Attendees: | Ismael Clark, Jared Hummer, Leandro Estevez, Victoria Fernandez, Felipe Arce Rivera, Akul Singh, Kevin Fontela, Raul Garcia Breijo, Jorge Segredo
Meeting Time: | 11/22/2021 5:30-6:00pm
Epics | Features | Tasks | Status | Assigned To | Priority
jTLEX Visualization
→ | Debug Code |  |  |  | 1
| → | Fix JSON duplicate partition bug | Completed | Jared Hummer, Ismael Clark
→ | Show Main Timeline |  |  |  | 3
| → | Connect timelines via connection point | In Progress | Jared Hummer, Leandro Estevez, Kevin Fontela, Raul Garcia Breijo
→ | Refactor Timeline |  |  |  | 2
| → | Agree on Visual Style | Completed | Jared Hummer, Ismael Clark, Leandro Estevez, Mustafa Ocal
| → | Figure out algorithm to stack nodes | Completed | Jared Hummer, Ismael Clark, Leandro Estevez
| → | Implement Code | Completed | Jared Hummer, Ismael Clark, Leandro Estevez
→ | Visualize Indeterminancies |  |  |  | 3
| → | Agree on Visual Style | Completed | Jared Hummer, Ismael Clark, Leandro Estevez, Mustafa Ocal
| → | Implement Code | In Progress | Jared Hummer, Leandro Estevez, Kevin Fontela, Raul Garcia Breijo
→ | Refactor Frontend Structure |  |  |  | 3
| → | Refactor Filenames | Completed | Jared Hummer, Ismael Clark, Leandro Estevez
| → | Refactor File Structure | In Progress | Jared Hummer, Leandro Estevez, Kevin Fontela, Raul Garcia Breijo
| → | Ensure successful commitment to VCS | In Progress | Jared Hummer, Leandro Estevez, Kevin Fontela, Raul Garcia Breijo
→ | Minor Bugs
| → | Make Nodes Static | In Progress | Leandro Estevez, Kevin Fontela, Raul Garcia Breijo
| → | Remove Time Point Connections | In Progress | Leandro Estevez, Kevin Fontela, Raul Garcia Breijo
| → | Make Connections Thicker | In Progress | Leandro Estevez, Kevin Fontela, Raul Garcia Breijo
pyTLEX Components
→ | Signal |  |  |  | 2
| → | Implement Code | Completed | Kevin Fontela
| → | Document Code | Completed | Kevin Fontela
| → | Test Code | Completed | Kevin Fontela
→ | Instance |  |  |  | 2
| → | Implement Code | Completed | Raul Garcia
| → | Document Code | Completed | Raul Garcia
| → | Test Code | Completed | Raul Garcia
→ | Timex |  |  |  | 2
| → | Implement Code | Completed | Jorge Segredo
| → | Document Code | Completed | Jorge Segredo
| → | Test Code | Completed | Jorge Segredo
→ | Event |  |  |  | 2
| → | Implement Code | Completed | Akul Singh
| → | Document Code | Completed | Akul Singh
| → | Test Code | Completed | Akul Singh
→ | Graph |  |  |  | 2
| → | Implement Code | Assigned | Jared Hummer, Felipe Arce
| → | Document Code | Assigned | Jared Hummer, Felipe Arce
| → | Test Code | Assigned | Jared Hummer, Felipe Arce
pyTLEX Logic
→ | TimeMl Parser |  |  |  | 1
| → | Implement Code | Completed | Victoria Fernandez, Jared Hummer, Ismael Clark
| → | Document Code | Completed | Victoria Fernandez, Jared Hummer, Ismael Clark
| → | Test Code | Completed | Victoria Fernandez, Jared Hummer, Ismael Clark
| → | Integrate Code | Assigned | Victoria Fernandez, Jared Hummer, Ismael Clark
→ | Indeterminacy Detector |  |  |  | 3
| → | Implement Code | Awaiting Assignment | Capstone 2 Student
| → | Document Code | Awaiting Assignment | Capstone 2 Student
| → | Test Code | Awaiting Assignment | Capstone 2 Student
→ | Inconsistency Detector |  |  |  | 3
| → | Implement Code | Assigned | Jared Hummer, Felipe Arce
| → | Document Code | Assigned | Jared Hummer, Felipe Arce
| → | Test Code | Assigned | Jared Hummer, Felipe Arce
→ | TCSP Solver |  |  |  | 1
| → | Implement Code | Completed | Jared Hummer, Akul Singh
| → | Document Code | In Progress | Jared Hummer, Akul Singh
| → | Test Code | In Progress | Jared Hummer, Akul Singh
→ | Partitioner |  |  |  | 1
| → | Implement Code | In Progress | Jared Hummer, Ismael Clark, Akul Singh
| → | Document Code | In Progress | Jared Hummer, Ismael Clark, Akul Singh
| → | Test Code | In Progress | Jared Hummer, Ismael Clark, Akul Singh
Initial Readings
Read Material
| → | Scrum Manual (Ch. 2 + 4) | Completed | Felipe Arce Rivera, Akul Singh, Kevin Fontela, Raul Garcia Breijo, Jorge Segredo | 1
| → | Temporal NLP Manual | Completed | Felipe Arce Rivera, Akul Singh, Kevin Fontela, Raul Garcia Breijo, Jorge Segredo | 1
| → | TimeML Annotation Guide | Completed | Felipe Arce Rivera, Akul Singh, Kevin Fontela, Raul Garcia Breijo, Jorge Segredo | 1
| → | TimeBank Corpus | Completed | Felipe Arce Rivera, Akul Singh, Kevin Fontela, Raul Garcia Breijo, Jorge Segredo | 1
| → | TLEX Paper | Completed | Felipe Arce Rivera, Akul Singh, Kevin Fontela, Raul Garcia Breijo, Jorge Segredo | 1
jTLEX Core
→ | Test Indeterminacies |  | Awaiting Elaboration | Unassigned | 5
pyTLEX Test Graphs
→ | Create Test Graphs
| → | Consistent Graph 6 | In Progress | Raul Garcia Breijo
| → | Consistent Graph 7 | In Progress | Kevin Fontela
| → | Consistent Graph 8 | In Progress | Jared Hummer
| → | Consistent Graph 9 | In Progress | Akul Singh
| → | Consistent Graph 10 | In Progress | Jorge Segredo