## Gantt Chart Template
Sprint # | STORY TITLE | TASK OWNER | START DATE | DUE DATE | PCT OF TASK COMPLETE |  |  |  |  | SPRINT 1 | [9 empty] | SPRINT 2 | [9 empty] | SPRINT 3 | [9 empty] | SPRINT 4 | [9 empty] | SPRINT 5 | [9 empty] | SPRINT 6 | [9 empty] | SPRINT 7
[6 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 1 |  |  |  |  | WEEK 2
1 | [5 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
| Setup Trello for Engineering team | Team | 2020-08-31 | 2020-09-13 | 100% | bar: WEEK 1 M to WEEK 1 T
| Read existing documentation | Team | 2020-08-31 | 2020-09-13 | 100% | bar: WEEK 1 M to WEEK 2 F
| Setup Development Environment | Team | 2020-08-31 | 2020-09-13 | 100% | bar: WEEK 1 M to WEEK 2 F
| Spike: Research and Learn Relevant Technologies | Team | 2020-08-31 | 2020-09-13 | 100% | bar: WEEK 1 M to WEEK 2 F
| Bug: Fix yarn install command | Team | 2020-08-31 | 2020-09-13 | 100% | bar: WEEK 1 M to WEEK 2 F
| Bug: Fix stuck on loading screen | Team | 2020-08-31 | 2020-09-13 | 100%
| Bug: Fix yarn gen command | Team | 2020-08-31 | 2020-09-13 | 100%
| Bug: Fix yarn seed command | Team | 2020-08-31 | 2020-09-13 | 100%
| Bug: Fix prisma.schema file syntax | Team | 2020-08-31 | 2020-09-13 | 100%
| Project Initiation | Team | 2020-08-31 | 2020-09-14 | 100% | bar: WEEK 1 M to WEEK 2 F
2
| Setup TravisCI or GH Actions integration with Github | Martyn Mallo | 2020-09-14 | 2020-09-27 | 100% | bar: WEEK 1 M to WEEK 2 F
| Implement guardian creation for students [FrontEnd] | Jessica Moreno | 2020-09-14 | 2020-09-27 | 50% | bar: WEEK 1 M to WEEK 1 F
| Fix instructor edit button | Martyn Mallo | 2020-09-14 | 2020-09-27 | 100% | bar: WEEK 1 M to WEEK 2 F
| Polish the codebase for the frontend, apply linting, formatting, etc | Jessica Moreno | 2020-09-14 | 2020-09-27 | 22%
| Add course page for admin | Carlos A. Barbachano | 2020-09-14 | 2020-09-27 | 56% | bar: WEEK 1 M to WEEK 1 F
| Log out button functionality | Carlos A. Barbachano | 2020-09-14 | 2020-09-27 | 10% | bar: WEEK 1 F to WEEK 2 F
| R&D Netlify deployment pipeline | Martyn Mallo | 2020-09-14 | 2020-09-27 | 100% | bar: WEEK 1 M to WEEK 2 F
3
| Delete student information after courses ends [FrontEnd] | Jessica Moreno | 2020-09-28 | 2020-10-11 | 100% | bar: WEEK 1 M to WEEK 2 M
| Delete student information after courses ends [BackEnd] | Martyn Mallo | 2020-09-28 | 2020-10-11 | 100% | bar: WEEK 1 M to WEEK 2 F
| Log out button functionality | Carlos A. Barbachano | 2020-09-28 | 2020-10-11 | 40% | bar: WEEK 1 M to WEEK 2 F
4
| Edit single student in course [Front End] | Jessica Moreno | 2020-10-12 | 2020-10-25 | 100% | bar: WEEK 1 M to WEEK 2 W
| Delete single student in course [Front End] | Jessica Moreno | 2020-10-12 | 2020-10-25 | 100% | bar: WEEK 1 M to WEEK 2 W
| Edit single student in course [Back End] | Carlos A. Barbachano | 2020-10-12 | 2020-10-25 | 100%
| Delete single student in course [Back End] | Martyn Mallo | 2020-10-12 | 2020-10-25 | 100% | bar: WEEK 1 M to WEEK 2 F
| Fix bug where page doesn’t refresh when deleting all students | Martyn Mallo | 2020-10-12 | 2020-10-25 | 50% | bar: WEEK 1 M to WEEK 2 F
| Add alert when username already exists | Martyn Mallo | 2020-10-12 | 2020-10-25 | 100% | bar: WEEK 1 M to WEEK 2 F
| Log out button functionality | Carlos A. Barbachano | 2020-10-12 | 2020-10-25 | 100% | bar: WEEK 1 M to WEEK 1 F
5
| Connect Delete and edit student front end and back end | Carlos A. Barbachano | 2020-10-26 | 2020-11-08 | 100% | bar: WEEK 1 R to WEEK 2 F
| Add a plus button to add a lesson | Jessica Moreno | 2020-10-26 | 2020-11-08 | 100% | bar: WEEK 1 M to WEEK 2 M
| Adding student email to student entity in PostgreSQL | Martyn Mallo | 2020-10-26 | 2020-11-08 | 100%
| Implement forgot password [FrontEnd] | Jessica Moreno | 2020-10-26 | 2020-11-08 | 100% | bar: WEEK 1 M to WEEK 2 F
| Fix bug where page doesn’t refresh when deleting all students | Martyn Mallo | 2020-10-26 | 2020-11-08 | 100% | bar: WEEK 1 M to WEEK 2 F
| Lesson creation doesn’t have a grade level associated with it | Carlos A. Barbachano | 2020-10-26 | 2020-11-08 | 100% | bar: WEEK 1 M to WEEK 1 W
| Style problems when lesson has a really long name bug | Jessica Moreno | 2020-10-26 | 2020-11-08 | 100% | bar: WEEK 1 M to WEEK 1 W
6
| Delete single student in course [Back End] | Carlos A. Barbachano | 2020-11-09 | 2020-11-23 | 100% | bar: WEEK 1 M to WEEK 1 W
| Implement forgot password [BackEnd] | Carlos A. Barbachano | 2020-11-09 | 2020-11-23 | 100% | bar: WEEK 1 W to WEEK 1 F
| Student can view edit button & Add course button | Martyn Mallo | 2020-11-09 | 2020-11-23 | 20% | bar: WEEK 1 M to WEEK 2 F
| Grades page for instructor [frontend] | Jessica Moreno | 2020-11-09 | 2020-11-23 | 100%
| Grades page for students [frontend] | Jessica Moreno | 2020-11-09 | 2020-11-23 | 100%
| Search lesson by title needs to filter the lessons object to match the input value | Jessica Moreno | 2020-11-09 | 2020-11-23 | 100% | bar: WEEK 1 M to WEEK 1 F
| Add delete button for deleting a lesson in admin view | Carlos A. Barbachano | 2020-11-09 | 2020-11-23 | 100% | bar: WEEK 2 M to WEEK 2 R
| Add delete button for updating the course form | Martyn Mallo | 2020-11-09 | 2020-11-23 | 20% | bar: WEEK 1 M to WEEK 2 F
| Allow lesson to be added into multiple courses | Carlos A. Barbachano | 2020-11-09 | 2020-11-23 | 20% | bar: WEEK 1 M to WEEK 1 F
| Add implementation to grey out lessons that have already been added to the lesson plan | Martyn Mallo | 2020-11-09 | 2020-11-23 | 100% | bar: WEEK 1 M to WEEK 2 F
7
| Final Deliverables Documentation | Team | 2020-11-24 | 2020-12-06 | 100% | bar: WEEK 1 M to WEEK 2 M
| Record Videos | Team | 2020-11-24 | 2020-12-06 | 100% | bar: WEEK 1 M to WEEK 2 W
| Create Poster | Team | 2020-11-24 | 2020-12-06 | 100% | bar: WEEK 1 M to WEEK 2 M
| Create Presentation Slides | Team | 2020-11-24 | 2020-12-06 | 100% | bar: WEEK 1 M to WEEK 1 F
| Shadow Project Wrap-up | Team | 2020-11-24 | 2020-12-06 | 100% | bar: WEEK 1 M to WEEK 2 F
| Approve Recorded Videos | Team | 2020-11-24 | 2020-12-06 | 100% | bar: WEEK 1 M to WEEK 2 F