## Sheet1
TASK | START TIME | END TIME | DURATION
Learn about Arduino Hardware | 2020-01-15 | 2020-01-27 | 12
Learn about programming Arduino | 2020-01-15 | 2020-01-27 | 12
Set up Arduino environment | 2020-01-15 | 2020-01-16 | 1
Look over Arduino documentation | 2020-01-15 | 2020-01-16 | 1
Read documents sent by PO about the spherification device | 2020-01-16 | 2020-01-17 | 1
Researching about Arduino sensors | 2020-01-16 | 2020-01-27 | 11
Review coding in C/C++ | 2020-01-17 | 2020-01-27 | 10
Examine hardware inside machine | 2020-01-21 | 2020-01-22 | 1
List parts needed to improve the current design | 2020-01-21 | 2020-01-24 | 3
Identify unnecessary parts in the current design | 2020-01-21 | 2020-01-22 | 1
Identify possible improvements to the device | 2020-01-21 | 2020-01-22 | 1
Review electronic circuits | 2020-01-24 | 2020-01-27 | 3
Acquire hands-on experience with Arduino | 2020-01-27 | 2020-02-06 | 10
Restore original electrical connections | 2020-01-30 | 2020-02-03 | 4
Restore original pipe connections | 2020-01-30 | 2020-02-03 | 4
Restore liquid mixer | 2020-01-30 | 2020-01-31 | 1
Reorganizing parts inside prototype | 2020-01-31 | 2020-02-04 | 4
Test prototype to see if it works after restoring | 2020-02-05 | 2020-02-06 | 1
Examine old source code | 2020-02-06 | 2020-02-10 | 4
Troubleshoot step motor for malfunction | 2020-02-06 | 2020-02-07 | 1
Add comments to methods created | 2020-02-07 | 2020-02-21 | 14
Add comments to the source code | 2020-02-10 | 2020-02-24 | 14
Add new functions to the source code | 2020-02-10 | 2020-02-24 | 14
Create a class to reflect LCD functions | 2020-02-11 | 2020-02-21 | 10
Add comments to variables | 2020-02-11 | 2020-02-21 | 10
Create a method to initialize and configure pumps | 2020-02-11 | 2020-02-12 | 1
Remove unused libraries from code | 2020-02-12 | 2020-02-14 | 2
Remove unused variables from code | 2020-02-12 | 2020-02-14 | 2
Redesigning layout of parts | 2020-02-12 | 2020-02-20 | 8
Research on volume sensors | 2020-02-18 | 2020-02-20 | 2
Upload code updates and test | 2020-02-21 | 2020-02-22 | 1
Install new blender (stomach) | 2020-03-02 | 2020-03-03 | 1
Debug source code to fix LCD buttons | 2020-03-02 | 2020-03-03 | 1
Research about railing system | 2020-03-03 | 2020-03-05 | 2
Mount railing system inside machine | 2020-03-05 | 2020-03-09 | 4
Mount pumps onto railing system | 2020-03-05 | 2020-03-10 | 5
Route wires from Arduino to pumps | 2020-03-05 | 2020-03-11 | 6
Route tubing from pumps to cartridges | 2020-03-05 | 2020-03-12 | 7
Debug source code to fix software bugs | 2020-03-11 | 2020-03-25 | 14
Improve stepping motor timings (frequency) | 2020-03-12 | 2020-03-25 | 13
Test machine with liquids prepared by PO | 2020-03-12 | 2020-03-13 | 1
Create sequence diagram on the use case of "start the machine" | 2020-03-13 | 2020-03-16 | 3
Research main issues for step motor "jump" | 2020-03-17 | 2020-03-18 | 1
Research on physical components of step motor in order to check for damage | 2020-03-17 | 2020-03-18 | 1
Research on main issues of step motor | 2020-03-17 | 2020-03-19 | 2
Research on upgrading tubing | 2020-03-17 | 2020-03-18 | 1
Research on how to troubleshoot step motor | 2020-03-19 | 2020-03-20 | 1
Create sequence diagram on the use case for "prime pumps" | 2020-03-19 | 2020-03-20 | 1
Create sequence diagram on the use case for "cleanse" | 2020-03-20 | 2020-03-23 | 3
Replace old tubing | 2020-03-23 | 2020-03-24 | 1
Test methods created in LCD class to debug issues | 2020-03-23 | 2020-03-25 | 2
Replace current tubing | 2020-03-23 | 2020-03-24 | 1
Create method to run step motor | 2020-03-24 | 2020-03-25 | 1
Clean step motor fully | 2020-03-24 | 2020-03-25 | 1
Create user-friendly variables | 2020-03-24 | 2020-03-26 | 2
Train PO on modifying machine timings with user-friendly variables created | 2020-03-27 | 2020-03-28 | 1
Label tubing to indicate if tubes are for input or output | 2020-03-30 | 2020-03-31 | 1
Design schematic diagram | 2020-03-30 | 2020-04-02 | 3
Drill necessary holes on blender's lid | 2020-03-31 | 2020-04-02 | 2
Improve routing of tubing | 2020-04-01 | 2020-04-06 | 5
Create class diagram | 2020-04-02 | 2020-04-08 | 6
Add more user-friendly variables | 2020-04-06 | 2020-04-08 | 2
Prepare machine for PO to pick up | 2020-04-07 | 2020-04-08 | 1
Help PO set up the machine | 2020-04-10 | 2020-04-13 | 3
Help PO set up Arduino IDE | 2020-04-10 | 2020-04-13 | 3
Update code to improve the geometry of pearls | 2020-04-10 | 2020-04-13 | 3
Make final touches to code | 2020-04-13 | 2020-04-14 | 1
create a README.txt file | 2020-04-13 | 2020-04-14 | 1
create an installation /maintenace guide | 2020-04-13 | 2020-04-21 | 8
create a poster(stephanie) | 2020-04-13 | 2020-04-25 | 12
create user manual document | 2020-04-14 | 2020-04-15 | 1
create daily scrum meeting file (stephanie) | 2020-04-14 | 2020-04-20 | 6
create daily scrum meeting file (Alex) | 2020-04-14 | 2020-04-25 | 11
Update user stories with acceptance criteria | 2020-04-15 | 2020-04-20 | 5
present planning meetings in final document | 2020-04-15 | 2020-04-25 | 10
edit user stories to be continuously numbered instead of reverting back to 1 every sprint | 2020-04-16 | 2020-04-20 | 4
create a shortcomings/wishlist | 2020-04-16 | 2020-04-17 | 1
create a poster(Alex) | 2020-04-17 | 2020-04-25 | 8
create introduction to include in presentation slides/final document | 2020-04-20 | 2020-04-21 | 1
write an abstract for the final document | 2020-04-20 | 2020-04-21 | 1
create Gnatt chart schedule | 2020-04-21 | 2020-04-25 | 4
include in slides what was required to implement solution (stephanie) | 2020-04-21 | 2020-04-25 | 4
include in slides what was required to implement solution (Alex) | 2020-04-21 | 2020-04-25 | 4
include in the slides what the system design -architecture | 2020-04-21 | 2020-04-25 | 4
include in the slides the detailed design of implementation (minimal class diagram) | 2020-04-21 | 2020-04-25 | 4
present user stories implemented in final document (stephanie) | 2020-04-21 | 2020-04-22 | 1
create a video that shows how to install, maintain, and how to start on the next revision | 2020-04-23 | 2020-04-24 | 1
create a video that shows what are the shortcomings of current software | 2020-04-23 | 2020-04-24 | 1
create a video that introduces the sofware solution | 2020-04-24 | 2020-04-25 | 1
create a video on how to use the software solution for each actor | 2020-04-24 | 2020-04-25 | 1
add videos to professor's account | 2020-04-24 | 2020-04-25 | 1
create an index.html with links to the videos | 2020-04-24 | 2020-04-25 | 1
present user stories implemented in final document (Alex) | 2020-04-24 | 2020-04-25 | 1
provide information about the current system in the final document | 2020-04-24 | 2020-04-25 | 1
provide system validation in the final document | 2020-04-24 | 2020-04-25 | 1
include a glossary in the final document | 2020-04-24 | 2020-04-25 | 1