## Sheet1
Sprint | Issue Key | Summary | Status | Start Date | End Date | Task | Start on Day | Duration
1 | user_story_0 | Environment Setup | Done | 2020-01-13 | 2020-01-26 | Environment Setup | 0 | 13
1 | user_story_1 | Understand Context of EForT and Learn About Forex Trading | Done | 2020-01-13 | 2020-01-26 | Understand Context of EForT and Learn About Forex Trading | 0 | 13
1 | user_story_2 | Running EForT in Local Environment | Done | 2020-01-13 | 2020-01-26 | Running EForT in Local Environment | 0 | 13
1 | user_story_3 | Get Azure DevOps and Github | Done | 2020-01-13 | 2020-01-26 | Get Azure DevOps and Github | 0 | 13
2 | user_story_4 | Test Previous Team’s Existing Functionality | Done | 2020-01-27 | 2020-02-09 | Test Previous Team’s Existing Functionality | 14 | 13
2 | user_story_5 | Previous Team’s Wishlist and Shortcomings | Done | 2020-01-27 | 2020-02-09 | Previous Team’s Wishlist and Shortcomings | 14 | 13
2 | user_story_6 | Review Previous Team’s Product Backlog | Done | 2020-01-27 | 2020-02-09 | Review Previous Team’s Product Backlog | 14 | 13
3 | user_story_7 | Add Fake Data | Done | 2020-02-10 | 2020-03-01 | Add Fake Data | 28 | 20
3 | user_story_8 | Finding Bugs and Document Process | Done | 2020-02-10 | 2020-03-01 | Finding Bugs and Document Process | 28 | 20
3 | user_story_9 | Test Previous Team’s Existing Functionality | Done | 2020-02-10 | 2020-03-01 | Test Previous Team’s Existing Functionality | 28 | 20
4 | user_story_10 | Remove Trader Controller TimeFrames Caching and AccountEquity Union | Done | 2020-03-02 | 2020-03-15 | Remove Trader Controller TimeFrames Caching and AccountEquity Union | 49 | 13
4 | user_story_11 | Use Forex Login Id for the GetAccountEquity function | Done | 2020-03-02 | 2020-03-15 | Use Forex Login Id for the GetAccountEquity function | 49 | 13
4 | user_story_12 | Accurate Data After Deletion on Account Equity Chart | Done | 2020-03-02 | 2020-03-15 | Accurate Data After Deletion on Account Equity Chart | 49 | 13
4 | user_story_13 | Time Frame Reset | Done | 2020-03-02 | 2020-03-15 | Time Frame Reset | 49 | 13
4 | user_story_14 | Navigate Between Different Chart Formats | Done | 2020-03-02 | 2020-03-15 | Navigate Between Different Chart Formats | 49 | 13
4 | user_story_15 | Moving Average Button Toggle State | Done | 2020-03-02 | 2020-03-15 | Moving Average Button Toggle State | 49 | 13
4 | user_story_16 | Volume Button Toggle State | Done | 2020-03-02 | 2020-03-15 | Volume Button Toggle State | 49 | 13
4 | user_story_17 | Crosshair Button Toggle State | Done | 2020-03-02 | 2020-03-15 | Crosshair Button Toggle State | 49 | 13
4 | user_story_18 | Share Chart Through Email | Done | 2020-03-02 | 2020-03-15 | Share Chart Through Email | 49 | 13
5 | user_story_19 | Accurate TimeFrame Toggling | Done | 2020-03-16 | 2020-03-29 | Accurate TimeFrame Toggling | 63 | 13
5 | user_story_20 | Save and Load Graph Templates | Done | 2020-03-16 | 2020-03-29 | Save and Load Graph Templates | 63 | 13
5 | user_story_21 | Update Database Using Entity Framework Migrations | Done | 2020-03-16 | 2020-03-29 | Update Database Using Entity Framework Migrations | 63 | 13
5 | user_story_22 | Update Team Wiki | Done | 2020-03-16 | 2020-03-29 | Update Team Wiki | 63 | 13
5 - 6 | user_story_23 | Save Settings Implicitly | Done | 2020-03-16 | 2020-04-12 | Save Settings Implicitly | 63 | 27
5 - 6 | user_story_24 | Balance Graph | Done | 2020-03-16 | 2020-04-12 | Balance Graph | 63 | 27
5 - 6 | user_story_25 | Toggling of Buttons Consistent with Settings | Done | 2020-03-16 | 2020-04-12 | Toggling of Buttons Consistent with Settings | 63 | 27
6 | user_story_26 | Template Entity Should Include Time Frame Being Viewed | Done | 2020-03-30 | 2020-04-12 | Template Entity Should Include Time Frame Being Viewed | 77 | 13
6 | user_story_27 | Collaborate with EFWE on Validation Story | Done | 2020-03-30 | 2020-04-12 | Collaborate with EFWE on Validation Story | 77 | 13
6 | user_story_28 | Database Migrations Load Stored Procedures | Done | 2020-03-30 | 2020-04-12 | Database Migrations Load Stored Procedures | 77 | 13
6 | user_story_29 | Display Chart No Data Available Message | Done | 2020-03-30 | 2020-04-12 | Display Chart No Data Available Message | 77 | 13
6 | user_story_30 | Visualize the Account Equity and Balance Graph with Real Data | Approved/ Not Complted | 2020-03-30 | 2020-04-27 | Visualize the Account Equity and Balance Graph with Real Data | 77 | 28
7 | user_story_31 | README.txt and other documents | Done | 2020-04-13 | 2020-04-26 | README.txt and other documents | 91 | 13
7 | user_story_32 | Final Project Documentation | Done | 2020-04-13 | 2020-04-26 | Final Project Documentation | 91 | 13
7 | user_story_33 | Update team wiki | Done | 2020-04-13 | 2020-04-26 | Update team wiki | 91 | 13
7 | user_story_34 | Final Presentation Powerpoint | Done | 2020-04-13 | 2020-04-26 | Final Presentation Powerpoint | 91 | 13
7 | user_story_35 | Final Poster | Done | 2020-04-13 | 2020-04-26 | Final Poster | 91 | 13
7 | user_story_36 | Create Intro Video | Done | 2020-04-13 | 2020-04-26 | Create Intro Video | 91 | 13
7 | user_story_37 | Create User Guide Video | Done | 2020-04-13 | 2020-04-26 | Create User Guide Video | 91 | 13
7 | user_story_38 | Create Installation Video | Done | 2020-04-13 | 2020-04-26 | Create Installation Video | 91 | 13
7 | user_story_39 | Create Shortcomings and Wishlist Video | Done | 2020-04-13 | 2020-04-26 | Create Shortcomings and Wishlist Video | 91 | 13