## Sheet1
User Story # | Description | Status by Fall2019 | Sprint # | Checked Status | Comments - Estefani | Comments - Nalin
3 | Add a toolbar setting that allows you to zoom in and out of the graph by one interval at a time. | Done | 1 |  |  | Works with both caching and without caching but with caching appears a bit wonky and might need to be removed
22 | Verify Moving Average toggle works with FAKE data | Done | 1 |  |  | Works but always resets to 4 hour view, even without the caching, Buggy, and no way to see if option is enabled or disabled. Am unable to toggle the EMA
10 | Run Website locally w/ fake data | Done | 1 |  |  | Works, able to do this
21 | Share Chart, (displaying fake data) through Email | Done | 1 |  |  | Does not work on server or on local, get an exception
19 | Display candlestick graph with correct data points using FAKE data | Done | 1 |  |  | Works
13 | Create view for graph | Done | 1 |  |  | Graph shows up when trader is signed in and there is data in the db
20 | Check navigation between each forex chart made from fake data (CandleStick, bar, line) | Done | 1 |  |  | Line graph shows up weird, charts only display with 4 hour view
17 | Verify Crosshair toggle works with FAKE data | Done | 1 |  |  | Works, crosshair can be toggled, but no way to see if it is enabled or disabled at a glance
14 | Verify accuracy of Highest, Lowest, Open, and Close of FAKE data graph | Done | 1 |  |  | Data lines up with what is in db, but what is purpose of isDeleted, the deleted ones also show up in my chart. (you probably shouldn't be able to delete history data points)
16 | Verify Volume toggle works with FAKE data | Done | 1 |  |  | Works, volume can be disabled but there is not a way to see if it is enabled or disabled at a glance
Sprint 3
27 | Fix data points for candlestick graph using FAKE data | Committed | 3
38 | Research CanvasJS Documentation | Committed | 3
39 | Work with EFWA team to learn database schema of EForT website. | Committed | 3 |  |  | Not needed for now
Sprint 4
40 | Fix Data Transfer issue when using Stored Procedure (FrontEnd or Backend issue?) | Committed | 4
42 | Make graphs in Trader home website dynamic. | Committed | 4
43 | Fix gap within datapoints in graph ( no weekend data) | Committed | 4
44 | Implement Api Function to getLoginIdFromForexId | Committed | 4
Shortcomings + Wishlist
23 | FA19-SC Fix graph defaulting to the hour, even when previously zoomed in | Wishlist
25 | FA19-SC Code cleanup and performance improvements | Wishlist
18 | FA19-SC Few bugs in LogAccountEquity function of Account EquityRepository | Wishlist
20 | FA19-SC Implement Balance Graph under the equity graph | Wishlist
21 | SU19-SC Graph zoom in and out | Wishlist
22 | SU19-SC User should be able to modify graph template | Wishlist
New and Approved FA 2019
15 | FA19 Test new features w/ real data on website
12 | FA19 Fix gap closing issue |  |  |  | Duplicate story
11 | FA19 Ensure that changing time intervals does not break range of values.
9 | FA19 Ensure that range of values on x-axis are displayed correctly using FAKE data |  |  |  | Duplicate Story
6 | FA19 Make sure "Reports" page works with demo FOREX account
5 | FA19 Ensure balance is displayed correctly for FOREX account
3 | FA19 Test candlestick graph with demo FOREX account provided by EFWA team
2 | FA19 Settings UI/Functionality
1 | FA19 Verify Moving Average toggle works with FAKE data
4 | FA19 Make sure switching FOREX accounts changes the actual account balance displayed
7 | FA19 Select FOREX account to display data in graph
8 | FA19 Share chart (displaying real data from demo FOREX account)
10 | FA19 Candlestick graph showing wrong axis data w/ fake data
13 | FA19 Download MetaTrader 5/ Learn about Financial Charts
14 | FA19 Visualize trader home page on public website
16 | FA19 Make web api function to Log Account Equity from MT5/Add Equity data to Database
17 | FA19 Implement MACD indicator in Trader home page
When there is a session timeout, waited too long and token expires, there should be a way to let user know, because they might try interacting with the UI and nothing happens then