## Sprints
Sprint Planning
Sprint 1: 9/9 - 9/20 | [9 empty] | Legend
Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Daily Scrum Meeting | DSM
2019-09-09 | 2019-09-10 | 2019-09-11 | 2019-09-12 | 2019-09-13 | 2019-09-16 | 2019-09-17 | 2019-09-18 | 2019-09-19 | 2019-09-20 | Sprint Pre-planning | SPP
DSM SPP - 1 | DSM SP - 1 | DSM POM | DSM | DSM SR | DSM SPP - 2 | DSM | DSM POM | DSM SP - 2 | DSM SRT - 1 | Sprint Planning | SP
[10 empty] | Sprint Review | SR
2019-09-09: Sprint 2: 9/23 - 10/4 | Sprint Retrospective | SRT
Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Daily Scrum Meetings | DSM
2019-09-23 | 2019-09-24 | 2019-09-25 | 2019-09-26 | 2019-09-27 | 2019-09-30 | 2019-10-01 | 2019-10-02 | 2019-10-03 | 2019-10-04 | Product Owner Meeting | POM
DSM SR - 2 | DSM | DSM POM | DSM | DSM | DSM SPP - 3 | DSM | DSM POM | DSM SP - 3 | DSM SRT - 2
Sprint 3: 10/7 - 10/18
Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri
2019-10-07 | 2019-10-08 | 2019-10-09 | 2019-10-10 | 2019-10-11 | 2019-10-14 | 2019-10-15 | 2019-10-16 | 2019-10-17 | 2019-10-18
DSM SR - 3 | DSM | DSM POM | DSM | DSM | DSM SPP - 4 | DSM | DSM POM | DSM SP - 4 | DSM SRT - 3
Sprint 4: 10/21 - 11/01
Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri
2019-10-21 | 2019-10-22 | 2019-10-23 | 2019-10-24 | 2019-10-25 | 2019-10-28 | 2019-10-29 | 2019-10-30 | 2019-10-31 | 2019-11-01
DSM SR - 4 | DSM | DSM POM | DSM | DSM | DSM SPP - 5 | DSM | DSM POM SPP - 6 | DSM SP - 5 | DSM SRT - 4
Sprint 5: 11/4 - 11/16
Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri
2019-11-04 | 2019-11-05 | 2019-11-06 | 2019-11-07 | 2019-11-08 | 2019-11-12 | 2019-11-13 | 2019-11-14 | 2019-11-15 | 2019-11-16
DSM SR - 5 | DSM | DSM POM | DSM | DSM | DSM SPP - 6 | DSM | DSM POM | DSM SP - 6 | DSM SRT - 5
Sprint 6: 11/18 - 11/29
Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri
2019-11-18 | 2019-11-19 | 2019-11-20 | 2019-11-21 | 2019-11-22 | 2019-11-25 | 2019-11-26 | 2019-11-27 | 2019-11-28 | 2019-11-29
DSM SR - 6 | DSM | DSM POM | DSM | DSM | DSM | DSM | DSM POM | DSM | DSM SRT - 6

## S1 - MM
Sprint 1 - Meeting Minutes
Sprint: | 1 |  | Sprint: | 1
Date: | 2019-09-09 |  | Date: | 2019-09-16
Attendees: | Melanie & Kent |  | Attendees: | Melanie & Kent
Start: | 11:00 |  | Start: | 11:00
End: | 11:15 |  | End: | 11:15
| Kent | Melanie |  | Kent | Melanie
What did you accomplish yesterday? | I was able to read React documentations | Research React documentation to be better prepared | What did you accomplish yesterday? | Set up github repo and looked into angular | Set up Github repo and research into Angular
What do you plan on doing today? | Continue checking react documentations | Continue with the Research | What do you plan on doing today? | Angular Tutorials as requested by our PO | Continue researching Angular
What obstacles did you encounter? | No Obstacles | No Obstacles | What obstacles did you encounter? | Learning curve for angular | Angular learning curve
Sprint: | 1 |  | Sprint: | 1
Date: | 2019-09-10 |  | Date: | 2019-09-17
Attendees: | Melanie & Kent |  | Attendees: | Melanie & Kent
Start: | 11:00 |  | Start: | 11:00
End: | 11:15 |  | End: | 11:15
| Kent | Melanie |  | Kent | Melanie
What did you accomlish yesterday? | I further read React documentations | Researched React Component Structure | What did you accomplish yesterday? | I did some angular tutorials | Completed Angular tutorials
What do you plan on doing today? | Do react tutorials | Continue researching about React designs | What do you plan on doing today? | Do research on other county's film permitting web apps | Gather Ideas and see how feasible they are for our purposes
What obstacles did you encounter? | Just the learning curve | No obstacles | What obstacles did you encounter? | Learning curve for angular | No obstacles
Sprint: | 1 |  | Sprint: | 1
Date: | 2019-09-11 |  | Date: | 2019-09-18
Attendees: | Melanie & Kent |  | Attendees: | Melanie & Kent
Start: | 11:00 |  | Start: | 11:00
End: | 11:15 |  | End: | 11:15
| Kent | Melanie |  | Kent | Melanie
What did you accomplish yesterday? | I was able to do react tutorials | I was able to go over some common design React practices. | What did you accomplish yesterday? | The team decided to create the project using React not Angular. | React was the finalized technology
What do you plan on doing today? | Meet with our Product Owner | Meet with PO | What do you plan on doing today? | 1.Read on React Documentations 2. Do React Tutorials | Familiarize myself more with React
What obstacles did you encounter? | None | No Obstacles | What obstacles did you encounter? | N/A | No obstacles
Sprint: | 1 |  | Sprint: | 1
Date: | 2019-09-12 |  | Date: | 2019-09-19
Attendees: | Melanie & Kent |  | Attendees: | Melanie & Kent
Start: | 11:00 |  | Start: | 11:00
End: | 11:15 |  | End: | 11:15
| Kent | Melanie |  | Kent | Melanie
What did you accomplish yesterday? | I did react tutorials and met with our PO | Continued React research and met with PO | What did you accomplish yesterday? | 1.Read on React Documentations 2. Do React Tutorials 3. Communicated with PO about using React | Communicated with PO about our ideas and progress. Continued Researching React
What do you plan on doing today? | Send my resume to our PO and review the Film Permitting website | Send resume to PO and review Film Permitting website and review other film permitting websites | What do you plan on doing today? | 1. Start Reading documentation of Material UI, as a framework for the Project | Go over Bootstrap vs Material UI.
What obstacles did you encounter? | No Obstacles | No Obstacles | What obstacles did you encounter? | React Learning Curve | No obstacles
Sprint: | 1 |  | Sprint: | 1
Date: | 2019-09-13 |  | Date: | 2019-09-20
Attendees: | Melanie & Kent |  | Attendees: | Melanie & Kent
Start: | 11:00 |  | Start: | 11:00
End: | 11:15 |  | End: | 11:15
| Kent | Melanie |  | Kent | Melanie
What did you accomplish yesterday? | I sent the required documents by our PO | Sent requested documents to PO and reviewed several websites for inspiration | What did you accomplish yesterday? | 1. Start Reading documentation of Material UI, as a framework for the Project | Decided Material UI was going to be final design framework
What do you plan on doing today? | Set up gitHub repo for our project and look into Angular | Set up GitHub repo and extra branches. Research Angular | What do you plan on doing today? | 1. Plan the Structure of the Project, how to divide the components 2. Review the current Strucuture of the One Stop System. | Divide components and start a design prototype
What obstacles did you encounter? | No Obstacles | No obstacles | What obstacles did you encounter? | React/Material UI Learning Curve | No obstacles

## S2 - MM
Sprint 2 - Meeting Minutes
Sprint: | 2 |  | Sprint: | 2
Date: | 2019-09-23 |  | Date: | 2019-09-30
Attendees: | Melanie & Kent |  | Attendees: | Melanie & Kent
Start: | 14:00 |  | Start: | 14:00
End: | 14:15 |  | End: | 14:15
| Kent | Melanie |  | Kent | Melanie
What did you accomlish yesterday? | Created User Stories after doing a demo with the old system. We listed all the necessary information required from the user to input | comments | What did you accomlish yesterday? | I started working on Step 1: I created the following components: - Search a company info - Select a company info - Add Company Info | Started working on Step 4. Create all appropiate fields
What do you plan on doing today? | Create a GitHub Repo with a Dev, Kent, and Melanie Branch | comments | What do you plan on doing today? | I plan on creating components for "Search a Company Info" - Grid, Box, Paper, Button, TextFields | Continue working on Step 4 and start working on Step 5.
What obstacles did you encounter? | No Obstacles | comments | What obstacles did you encounter? | Routing the Step 1 components to ParentForm | No Obstacles.
Sprint: | 2 |  | Sprint: | 2
Date: | 2019-09-24 |  | Date: | 2019-10-01
Attendees: | Melanie & Kent |  | Attendees: | Melanie & Kent
Start: | 14:00 |  | Start: | 14:00
End: | 14:15 |  | End: | 14:15
| Kent | Melanie |  | Kent | Melanie
What did you accomlish yesterday? | Created the repository in Gihub - Created a Development Branch - Created 'Kent's Branch" | Created repo in Github for final website design. Created Melanie branch. | What did you accomlish yesterday? | I created Grid, Paper, Button, and TextFields for the "Search a company info" component | Created Step 5 and finalized Step 4 Component
What do you plan on doing today? | Create the Shell of the System, follow the structure of the old system | Create shell system following old structure | What do you plan on doing today? | I will work on the first part of the component which is entering a Production Company Name on the textfield with "Search" and "add" buttons | Continue working on Step 5 and start working on Step 6 Component.
What obstacles did you encounter? | React Learning Curve | No obstacle | What obstacles did you encounter? | I struggled on creating the texfields using Material UI | Implementing some Material UI features
Sprint: | 2 |  | Sprint: | 2
Date: | 2019-09-25 |  | Date: | 2019-10-02
Attendees: | Melanie & Kent |  | Attendees: | Melanie & Kent
Start: | 14:00 |  | Start: | 14:00
End: | 14:15 |  | End: | 14:15
| Kent | Melanie |  | Kent | Melanie
What did you accomlish yesterday? | 1.Created the main shell of the system - The parent form will house all of the Steps (components) | Create main shell with footer and header. | What did you accomlish yesterday? | I created the "Search Company" component using Grid , TextFields, Box, Paper, Button | Gathered information about shell design. Finalized Step 5 Component.
What do you plan on doing today? | 2. Create the Step 1,2,3,4,5,6,7 Components | Create Step Components based on old structure | What do you plan on doing today? | I plan on working on the 2nd component of Step 1, "Search Company" Info using TexField, Button, Grid, Box, paper | Will Work on Step 6 Component and try to finalize Grid layout.
What obstacles did you encounter? | No Obstacles. | No Obstacles. | What obstacles did you encounter? | Creating the Grid layout is difficult, the width of the whole form has to be 851px | Grid layout is difficult to set up
Sprint: | 2 |  | Sprint: | 2
Date: | 2019-09-26 |  | Date: | 2019-10-03
Attendees: | Melanie & Kent |  | Attendees: | Melanie & Kent
Start: | 14:00 |  | Start: | 14:00
End: | 14:15 |  | End: | 14:15
| Kent | Melanie |  | Kent | Melanie
What did you accomlish yesterday? | Created the Step 1,2,3,4,5,6,7 Components | Created all Step Components | What did you accomlish yesterday? | I worked on the 2nd component of Step 1, "Search Company" Info using TexField, Button, Grid, Box, paper | Worked on Step 6 and the master shell layout
What do you plan on doing today? | 1. Divide the user stories with Melanie 2. Meet with PO to go over the current plan, and our user stories | Divide components with Kent Meet with PO about progrress | What do you plan on doing today? | I plan on working on the 3nd component of Step 1, "CompanyInfoAdd" Info using TexField, Button, Grid, Box, paper | Finalize Step 6 and grid layout
What obstacles did you encounter? | Creating the user stories Getting information from the current system | Getting information from current system. | What obstacles did you encounter? | The grid layout is getting out of wack, I need to be able to find a way to modularize the components | Grid layout still proving to be difficult
Sprint: | 2 |  | Sprint: | 2
Date: | 2019-09-27 |  | Date: | 2019-10-04
Attendees: | Melanie & Kent |  | Attendees: | Melanie & Kent
Start: | 14:00 |  | Start: | 14:00
End: | 14:15 |  | End: | 14:15
| Kent | Melanie |  | Kent | Melanie
What did you accomlish yesterday? | We distributed the user stories and planned which components are assigned to us | comments | What did you accomlish yesterday? | I worked on the 3nd component of Step 1, "CompanyInfoAdd" Info using TexField, Button, Grid, Box, paper | Finalize Step 6 component and tried adjusting grid layout
What do you plan on doing today? | I will start working on Step 1 component - ProductionCompanyInfo | comments | What do you plan on doing today? | I plan on fixing the Grid Layout I plan on creating a ButtonGroup component for the "Search" and "add" buttons | Will finalize the Display Information Component
What obstacles did you encounter? | None | comments | What obstacles did you encounter? | The Grid Layout is still not working, I will try on encapsulating all components within the box and set the width to 851px | Grid layout still not completed.

## S3 - MM
Sprint 3 - Meeting Minutes
Sprint: | 3 |  | Sprint: | 3
Date: | 2019-10-07 |  | Date: | 2019-10-14
Attendees: | Melanie & Kent |  | Attendees: | Melanie & Kent
Start: | 13:00 |  | Start: | 13:00
End: | 13:15 |  | End: | 13:15
| Kent | Melanie |  | Kent | Melanie
What did you accomlish yesterday? | I committed my current progress with my branch on GitHub. I worked on fixing the form layout but putting the components within a Box Component I worked on the 3rd page of Step 1: CompanyInfoAdd | Step 4,5,6 and Display Component skeleton finalized. Continue working on Grid Layout. | What did you accomlish yesterday? | My team discussed the pros and cons of using Material UI and Bootstrap, we ultimately decided on sticking with Material UI. | Discussed Material UI vs Bootstrap. Stayed with Material UI. Worked on Stepper feature.
What do you plan on doing today? | I plan on finishing up the 'CompanyInfoAdd" component within Step 1. - I will work on editing the sizes of the text fields to make them fit within the layout - I need to add the following textfields: | Start working on Stepper functionality. | What do you plan on doing today? | 1. Set up a meeting with our PO to review our progress. 2. Verify and review user stories with our PO 3. Start working on Step 2 | Meet with PO and create functions to traverse through steps, and updating the step icon.
What obstacles did you encounter? | The grid layout is still a problem, the Box component mdid not work so I will use a Parent Grid to put all the components in it | Learning Curve for Stepper functionality | What obstacles did you encounter? | Learning curve with Material UI/React | Learning Curve Stepper
Sprint: | 3 |  | Sprint: | 3
Date: | 2019-10-08 |  | Date: | 2019-10-15
Attendees: | Melanie & Kent |  | Attendees: | Melanie & Kent
Start: | 13:00 |  | Start: | 13:00
End: | 13:15 |  | End: | 13:15
| Kent | Melanie |  | Kent | Melanie
What did you accomlish yesterday? | I finished adding the components for "CompanyInfoAdd" The text fields are well aligned with each other. | Worked on Stepper Functionality Implementation. | What did you accomlish yesterday? | We were able to contact our PO and setup a meeting time I started working on Step 2 which is "ProductionCompanyContactSearch" | Set up some functions for the Stepper to work.
What do you plan on doing today? | I need to rearrange the buttons, somehow they are not aligning perfectly with the rest of the components | Continue working on Stepper Functionality | What do you plan on doing today? | Add components on "ProductionCompanyContactSearch" Buttons, Cards, Grids, Paper, Box, TextFields, Typography | Continue working on the stepper functions pending and create switch cases for the step and the stepper independently.
What obstacles did you encounter? | Aligning components | Learning Curve for Stepper Functionality | What obstacles did you encounter? | N/A | Step and Stepper should be different functions
Sprint: | 3 |  | Sprint: | 3
Date: | 2019-10-09 |  | Date: | 2019-10-16
Attendees: | Melanie & Kent |  | Attendees: | Melanie & Kent
Start: | 13:00 |  | Start: | 13:00
End: | 13:15 |  | End: | 13:15
| Kent | Melanie |  | Kent | Melanie
What did you accomlish yesterday? | I worked on aligning the buttons with the rest of the components. I put each buttons in a grid as a grid item xs=6 | Worked on Stepper Functionality. | What did you accomlish yesterday? | I added the following components to "ProductionCompanyInfoSearch" page | Created independent stepper and step functions Created test cases to make sure it works properly.
What do you plan on doing today? | I will work on styling the buttons to match the look and feel our PO wants | Continue working on Stepper Functionality through another approach. | What do you plan on doing today? | I will work on the stylings of this page, to align the textfields and buttons with the textbox containing the definition of the step and its title | Test the cases created yesterday and correct any discrepancies.
What obstacles did you encounter? | Position components within the page | Learning Curve for Stepper Functionality. | What obstacles did you encounter? | Fixing the layout of "ProductionCompanyInfoContact" page | No obstacles.
Sprint: | 3 |  | Sprint: | 3
Date: | 2019-10-10 |  | Date: | 2019-10-17
Attendees: | Melanie & Kent |  | Attendees: | Melanie & Kent
Start: | 13:00 |  | Start: | 13:00
End: | 13:15 |  | End: | 13:15
| Kent | Melanie |  | Kent | Melanie
What did you accomlish yesterday? | I worked on styling the buttons and textfields for Step 1, we need to show our PO if he likes the design | Was able to implement stepper functionality. | What did you accomlish yesterday? | I continued on working on the styling of the page, it is not 100% finish, some textfields are not showing 100% width, xs=12 within the grid | Tested the stepper feature. Finalized the user story.
What do you plan on doing today? | I will look into Formik and Bootstrap to see if it’s a better alternative | Approach used for Stepper functionality created an error will try to solve today. | What do you plan on doing today? | Merge current changes with Melanie's branch and into the development branch | Will work on styling of the components 4,5,6 and Display and merge current progress with Kent
What obstacles did you encounter? | Material UI styling error | Stepper functionality error | What obstacles did you encounter? | Layout issues with the grid items | No obstacles.
Sprint: | 3 |  | Sprint: | 3
Date: | 2019-10-11 |  | Date: | 2019-10-18
Attendees: | Melanie & Kent |  | Attendees: | Melanie & Kent
Start: | 13:00 |  | Start: | 13:00
End: | 13:15 |  | End: | 13:15
| Kent | Melanie |  | Kent | Melanie
What did you accomlish yesterday? | I explored Formik and Bootstrap | Worked on Stepper Functionality. | What did you accomlish yesterday? | Merge the changes for both of Melanie's and I branches into the development branch | Styled the components 4,5,6 and Display and also merged progress with Kent on Github.
What do you plan on doing today? | I need to discuss with Melanie if we should change our framework to Bootstrap | Continue working on Stepper functionality | What do you plan on doing today? | There are some conflicts with melanie's branch so we need to be able to merge our branch to development. I have to add Melanie's changes to my branch in order to add it to the development branch | We had some conflicts merging so we will continue working] on that today and styling of components.
What obstacles did you encounter? | Some Material UI components are difficult to edit | Step 1 not showing correctly in Step feature | What obstacles did you encounter? | Merging conflicts | merging conflicts

## S4 - MM
Sprint 4 - Meeting Minutes
Sprint: | 4 |  | Sprint: | 4
Date: | 2019-10-21 |  | Date: | 2019-10-28
Attendees: | Melanie & Kent |  | Attendees: | Melanie & Kent
Start: | 13:00 |  | Start: | 13:00
End: | 13:15 |  | End: | 13:15
| Kent | Melanie |  | Kent | Melanie
What did you accomlish yesterday? | My team was working on the merging conflicts that emerged when we tried merging our branches | We worked on the merging conflicts that emerged and on styling of components. | What did you accomlish yesterday? | 1. I committed and pushed my changes to my branch and merged it to the development branch 2. I created a card with the title of the page and information of the step 3. I started adding the text fields for this page, "ProductionCompanyContactInfoAdd" | comments
What do you plan on doing today? | I will continue on working with the merging conflcits but I will move on and keep on working on the page | Continue working on merging conlicts and styling of components. | What do you plan on doing today? | I will continue working on the page: adding styling the textfields | comments
What obstacles did you encounter? | No Obstacles | No obstacles. | What obstacles did you encounter? | No obstacles | comments
Sprint: | 4 |  | Sprint: | 4
Date: | 2019-10-22 |  | Date: | 2019-10-29
Attendees: | Melanie & Kent |  | Attendees: | Melanie & Kent
Start: | 13:00 |  | Start: | 13:00
End: | 13:15 |  | End: | 13:15
| Kent | Melanie |  | Kent | Melanie
What did you accomlish yesterday? | I was able to resolve the merging conflicts with my branch and merge my branch into the development branch. | Merging conflicts were resolved and I continued working on styling of components. | What did you accomplish yesterday? | I continued working on the styling and layout of the text fields within the page. I tried implemeneting grids by putting textfield components within grids and I found that it is the besdt way to layout the textfields. | comments
What do you plan on doing today? | I will work on the card component of the "ProductionCompanyContactInfo", the typography of the text is not aligning properly with the grid. I will work on the text field components of the page as well | Work on the data transfer functions from child to parent function and viceversa | What do you plan on doing today? | I plan on adding and styling the buttons: CANCEL, ADD | comments
What obstacles did you encounter? | I had difficulty in aligning the card and textfield component | No obstacles. | What obstacles did you encounter? | Styling and the layout of the textfields, some textfields did not want to position itself where I want it to | comments
Sprint: | 1 |  | Sprint: | 4
Date: | 1900-01-03 |  | Date: | 2019-10-30
Attendees: | Melanie & Kent |  | Attendees: | Melanie & Kent
Start: | 13:00 |  | Start: | 13:00
End: | 13:15 |  | End: | 13:15
| Kent | Melanie |  | Kent | Melanie
What did you accomlish yesterday? | I was able to finish the styling of "productionCompanyContacInfo" Search I was able to finish the issues with the card component on "ProductionCompanyContactInfoList" | Worked on the data transfer functions from child to parent function and viceversa | What did you accomlish yesterday? | I ifnished the styling and layout of the Textfields and Buttons | comments
What do you plan on doing today? | I plan on working on the textfield components of "productionCompanyContactInfoList" | Continue working on the data transfer functions from child to parent function and viceversa | What do you plan on doing today? | I plan on committing and pushing my changes to our repo, and start working on Step 3 of the form which is the "ProductionContactInformation" | comments
What obstacles did you encounter? | No obstacles | Learning curve to pass data | What obstacles did you encounter? | No Obstacles | comments
Sprint: | 4 |  | Sprint: | 4
Date: | 2019-10-24 |  | Date: | 2019-10-31
Attendees: | Melanie & Kent |  | Attendees: | Melanie & Kent
Start: | 13:00 |  | Start: | 13:00
End: | 13:15 |  | End: | 13:15
| Kent | Melanie |  | Kent | Melanie
What did you accomlish yesterday? | I finished styling the text field components of "ProductionCompanyContactinfoList" page, we liked the idea of making it more 'dense' to have a more minimalistic feel on the page | Worked on the data transfer functions from child to parent function and viceversa | What did you accomlish yesterday? | 1.I committed and pushed my changes to the development branch 2. I started working on the first page of step 3 which is "ProductionContactInfo" 3. I added the Card component with the title and added typography component for the details of the page | Able to pass data from parent to child component.
What do you plan on doing today? | I plan on styling the buttons on the "ProductionCompanyContactInfoList" | continue working on the data transfer functions from child to parent function and viceversa | What do you plan on doing today? | I plan on adding text fields components on the page I plan on adding button components as well | Modify functions so that this transfer functionality is available in each component.
What obstacles did you encounter? | The button layout does not align with the rest of the text fields | Learning curve for data transfer | What obstacles did you encounter? | No Obstacles | Learning Curve of Data transfer
Sprint: | 4 |  | Sprint: | 4
Date: | 2019-10-25 |  | Date: | 2019-11-01
Attendees: | Melanie & Kent |  | Attendees: | Melanie & Kent
Start: | 13:00 |  | Start: | 13:00
End: | 13:15 |  | End: | 13:15
| Kent | Melanie |  | Kent | Melanie
What did you accomlish yesterday? | I worked on the styling of the buttons, I switch from "Button Groups" to just individual button components | Worked on the data transfer functions from child to parent function and viceversa | What did you accomlish yesterday? | I added the text fields and button components | Implemented function to pass data from parent to child component.
What do you plan on doing today? | I plan on committing my chnages and merging it to melanie's branch I will start working on the "ProductionCompanyContactInfoAdd" | continue working on the data transfer functions from child to parent function and viceversa | What do you plan on doing today? | I plan on reviewing my progress with melanie's progress and merge our branches to see if there are conflicts. If there are conflicts, we are going to work on it before moving on to the next sprints | Merge progess with Kent's on Github.
What obstacles did you encounter? | The button group was giving issues on the layout of the page so I tried using individual button components and putting them on individual grids | Learning Curve for Data Transfer | What obstacles did you encounter? | No obstacles | No obstacles.

## S5 - MM
Sprint 5 - Meeting Minutes
Sprint: | 5 |  | Sprint: | 5
Date: | 2019-11-04 |  | Date: | 2019-11-11
Attendees: | Melanie & Kent |  | Attendees: | Melanie & Kent
Start: | 13:00 |  | Start: | 13:00
End: | 13:15 |  | End: | 13:15
| Kent | Melanie |  | Kent | Melanie
What did you accomlish yesterday? | My team reviewed our progress and fixed our mergin conflicts | comments | What did you accomlish yesterday? | I was able to solve merging conflicts and push my changes to the development branch | comments
What do you plan on doing today? | I plan on starting the 2nd page of step 3 which is "ProductionContactInfoList" | comments | What do you plan on doing today? | I will work on the last page of step 3: ProductionContactInfoAdd | comments
What obstacles did you encounter? | No Obstacles | comments | What obstacles did you encounter? | No Obstacles | comments
Sprint: | 5 |  | Sprint: | 5
Date: | 2019-11-05 |  | Date: | 2019-11-12
Attendees: | Melanie & Kent |  | Attendees: | Melanie & Kent
Start: | 14:00 |  | Start: | 13:00
End: | 14:15 |  | End: | 13:15
| Kent | Melanie |  | Kent | Melanie
What did you accomlish yesterday? | I added the card component on the "ProductionContactinfoList" with th title of the page and typography component with the details of the page | Finalized styled desgin of components and stepper. Were able to merge code together. | What did you accomlish yesterday? | I added the card component on the "ProductionContactinfoAdd" with the title of the page and typography component with the details of the page | Able to merge code together. Worked on animations for each step transition
What do you plan on doing today? | I will add the textfield and Button components | I will work on the expansion and collapse feature the summary box. | What do you plan on doing today? | I will add the textfield and Button components | Work on animations for each step
What obstacles did you encounter? | No obstacles | No obstacles. | What obstacles did you encounter? | comments | Learning curve for animations using html
Sprint: | 5 |  | Sprint: | 5
Date: | 2019-11-06 |  | Date: | 2019-11-13
Attendees: | Melanie & Kent |  | Attendees: | Melanie & Kent
Start: | 14:00 |  | Start: | 13:00
End: | 14:15 |  | End: | 13:15
| Kent | Melanie |  | Kent | Melanie
What did you accomlish yesterday? | I added the textfield and button components of the "productionContactInfoList" page | Worked on the expand/collapse feauture of summary box | What did you accomlish yesterday? | I added the textfield and button components of the "productionContactInfoAdd" page | Worked on animations using html
What do you plan on doing today? | I plan on working of the styling and layout of textfield and button components | Continue working on the expand/collapse feature of summary box | What do you plan on doing today? | I plan on working of the styling and layout of textfield and button components | Continue working on animation feature
What obstacles did you encounter? | I encountered grid layout issues | No obstacles. | What obstacles did you encounter? | I encountered grid layout issues | Learning Curve for animations
Sprint: | 5 |  | Sprint: | 5
Date: | 2019-11-07 |  | Date: | 2019-11-14
Attendees: | Melanie & Kent |  | Attendees: | Melanie & Kent
Start: | 14:00 |  | Start: | 13:00
End: | 14:15 |  | End: | 13:15
| Kent | Melanie |  | Kent | Melanie
What did you accomlish yesterday? | I worked on the styling and layout of Text Field and Button components | Finished the expand/collapse of the summary box | What did you accomlish yesterday? | I worked on the styling and layout of Text Field and Button components | Was able to finish the animation feature
What do you plan on doing today? | I plan on committing and pushing my changes on github | Work on the animations for each step transition and merge code with Kent. | What do you plan on doing today? | I plan on committing and pushing my changes on github | Test the animation feature and merge code.
What obstacles did you encounter? | No obstacles | No Obstacles. | What obstacles did you encounter? | No obstacles | No obstacles.
Sprint: | 5 |  | Sprint: | 5
Date: | 2019-11-08 |  | Date: | 2019-11-15
Attendees: | Melanie & Kent |  | Attendees: | Melanie & Kent
Start: | 2:00 PM 2:15 PM |  | Start: | 13:00
End: |  |  | End: | 13:15
| Kent | Melanie |  | Kent | Melanie
What did you accomlish yesterday? | I was able to review my changes with melanie, we tried merging our branches but there were some clinflicts | Some conflicts with the merging of codes. Worked on animation feature. | What did you accomlish yesterday? | I was able to review my changes with melanie, we tried merging our branches but there were some conflicts | Tried merging code with Kent, finished animation after fixing some errors after testing was completed
What do you plan on doing today? | I will work on the merge conflicts so I can push my changes to the development branch | Work on the animation and solve the merging conflicts | What do you plan on doing today? | I will work on the merge conflicts so I can push my changes to the development branch | Work on the merge conflicts
What obstacles did you encounter? | Merge conflicts | Merge conflicts | What obstacles did you encounter? | Merge conflicts | Merge conflicts

## S6 - MM
Sprint 6 - Meeting Minutes
Sprint: | 6 |  | Sprint: | 6
Date: | 2019-11-18 |  | Date: | 2019-11-25
Attendees: | Melanie & Kent |  | Attendees: | Melanie & Kent
Start: | 13:00 |  | Start: | 13:00
End: | 13:15 |  | End: | 13:15
| Kent | Melanie |  | Kent | Melanie
What did you accomlish yesterday? | My team reviewed our progress and fixed our merging conflicts | Reviewed progress and fix merging conflicts. | What did you accomlish yesterday? | I implemented the expanion panel component on the summary page of the form | Worked on expansion panel and design of step components.
What do you plan on doing today? | I plan on creating the general layout of the form per PO's request: Header, Body, Footer | Continue working on the design of each component and layout | What do you plan on doing today? | I will commit and merge my changes to the development branch | Commit and merge changes to development
What obstacles did you encounter? | No Obstacles | No obstacles. | What obstacles did you encounter? | No obstacles | No obstacles.
Sprint: | 6 |  | Sprint: | 6
Date: | 2019-11-19 |  | Date: | 2019-11-26
Attendees: | Melanie & Kent |  | Attendees: | Melanie & Kent
Start: | 13:00 |  | Start: | 15:00
End: | 13:15 |  | End: | 15:15
| Kent | Melanie |  | Kent | Melanie
What did you accomlish yesterday? | I created a layout folder containing the header component, parentform component, and footer component | Worked on design and master layout of web application | What did you accomlish yesterday? | I committed and merged my changes with melanie's branch but we encountered merging conflicts | Mergin conflicts encountered, worked on solving them
What do you plan on doing today? | I plan on resizing the header and footer component to match the width of the parentform component | Continue working on design and layout of each component | What do you plan on doing today? | I will fix the merging conflicts which emerged when merging our branches together | Work on solving merge conflicts.
What obstacles did you encounter? | Rezizing the components | No obstacles. | What obstacles did you encounter? | Merging conflicts | Merge conflicts
Sprint: | 6 |  | Sprint: | 6
Date: | 2019-11-20 |  | Date: | 2019-11-27
Attendees: | Melanie & Kent |  | Attendees: | Melanie & Kent
Start: | 15:00 |  | Start: | 15:00
End: | 15:15 |  | End: | 15:15
| Kent | Melanie |  | Kent | Melanie
What did you accomlish yesterday? | I resized the header and footer components | Worked on design and master layout of web application | What did you accomlish yesterday? | I fixed the mergin conflix from out last merge | Fixed merging conflict.
What do you plan on doing today? | I plan on working on the Summary Page of the form | Work on summary page component. | What do you plan on doing today? | I will add a Date and Time input field components on the production info page | Finalize design for text fields in each component
What obstacles did you encounter? | No obstacles | No obstacles. | What obstacles did you encounter? | The Date and Time components is not able to select a user input | No obstacles.
Sprint: | 6 |  | Sprint: | 6
Date: | 2019-11-21 |  | Date: | 2019-11-28
Attendees: | Melanie & Kent |  | Attendees: | Melanie & Kent
Start: | 15:00 |  | Start: | 15:00
End: | 15:15 |  | End: | 15:15
| Kent | Melanie |  | Kent | Melanie
What did you accomlish yesterday? | I started working on the summary page of the form | Worked on summary page component | What did you accomlish yesterday? | I implemented the date and time input component on the form | Finalized text field design in each component.
What do you plan on doing today? | I need to continue working the summary form. I would like to make it more minimalistic I will do my research and look at what other counties/cities One Stop Film form look like | Continue working on the summary page component and design layout of components. | What do you plan on doing today? | I will add a "Multiline" component as a text field | Finalize component design, summary box, stepper, and data transfer.
What obstacles did you encounter? | I struggled with the design of the form. I would like ti to look more minimalistic and aesthetic | Gathering ideas to make summary page as aesthetic as possible | What obstacles did you encounter? | no obstacles | No obstacles
Sprint: | 6 |  | Sprint: | 6
Date: | 2019-11-22 |  | Date: | 2019-11-29
Attendees: | Melanie & Kent |  | Attendees: | Melanie & Kent
Start: | 15:00 |  | Start: | 15:00
End: | 15:15 |  | End: | 15:15
| Kent | Melanie |  | Kent | Melanie
What did you accomlish yesterday? | I researched other one stop film forms from other counties I decided to use the ExpansionPanel component from Material UI library | We decided to use the ExpansionPanel component from Material UI. Worked on summary box and component desgin. | What did you accomlish yesterday? | I added and implemented a multiline component on the form for multiline text inputs | Finalized components design, stepper, summary box, and data trasnfer.
What do you plan on doing today? | I plan on implementing the expansion panel component | Implement expansion panel and finalize design for components. | What do you plan on doing today? | I plan on fixing remaining bugs and doing unit testing | Fix bugs and complete unit testing
What obstacles did you encounter? | No obstacles | No obstacles. | What obstacles did you encounter? | No obstacles | No obstacles.