## Christopher Whilar
Sprint # | Day of Week | Date | Check In | Check Out | Lunch In | Lunch Out | Short description of your work | Daily Hours | Weekly Hours | Overtime Hours | Approval
0 | 1
| Saturday | 2017-01-07 | [5 empty] | 0:00
| Sunday | 2017-01-08 | [5 empty] | 0:00
| Monday | 2017-01-09 | [5 empty] | 0:00
| Tuesday | 2017-01-10 | [5 empty] | 0:00
| Wednesday | 2017-01-11 | [5 empty] | 0:00
| Thusday | 2017-01-12 | [5 empty] | 0:00
| Friday | 2017-01-13 | [5 empty] | 0:00
1 | 2 | [6 empty] | 0:00
| Saturday | 2017-01-14 | [5 empty] | 0:00
| Sunday | 2017-01-15 | [5 empty] | 0:00
| Monday | 2017-01-16 | 12:00 | 17:00 |  |  | Watch tutorial Videos | 5:00
| Tuesday | 2017-01-17 | 12:00 | 17:00 |  |  | Watch tutorial Videos | 5:00
| Wednesday | 2017-01-18 | 12:00 | 17:00 |  |  | Learn about Scrum and how to use Mingle | 5:00
| Thusday | 2017-01-19 | 12:00 | 17:00 |  |  | Understand Github and Version Control | 5:00
| Friday | 2017-01-20 | [5 empty] | 0:00
| 3 | [6 empty] | 0:00
| Saturday | 2017-01-21 | [5 empty] | 0:00
| Sunday | 2017-01-22 | [5 empty] | 0:00
| Monday | 2017-01-23 | 12:00 | 17:00 |  |  | Review Software Engineering and Testing Concepts | 5:00
| Tuesday | 2017-01-24 | [5 empty] | 0:00
| Wednesday | 2017-01-25 | 10:30 | 15:30 |  |  | Met with Brian on hangouts and did research about the company's API and SDK | 5:00
| Thusday | 2017-01-26 | [5 empty] | 0:00
| Friday | 2017-01-27 | [5 empty] | 0:00
2 | 4 | [6 empty] | 0:00
| Saturday | 2017-01-28 | [5 empty] | 0:00
| Sunday | 2017-01-29 | [5 empty] | 0:00
| Monday | 2017-01-30 | 14:00 | 18:00 |  |  | Do comprehensive research on SDK and API creation | 4:00
| Tuesday | 2017-01-31 | 14:00 | 18:00 |  |  | Do comprehensive research on SDK and API creation | 4:00
| Wednesday | 2017-02-01 | 14:00 | 18:00 |  |  | Workn on SDK and API Report | 4:00
| Thusday | 2017-02-02 | 14:00 | 18:00 |  |  | Work on SDK and API report. Provide simple samples, languages, services, and step by step process | 4:00
| Friday | 2017-02-03 | 14:00 | 18:00 |  |  | Met with Brian and the leading engineer Neil on hangouts to talk about the project. Also worked on SDK and API report. | 4:00
| 5 | [6 empty] | 0:00
| Saturday | 2017-02-04 | 12:00 | 16:00 |  |  | Run C++ code examples on Android Studio using JNI | 4:00
| Sunday | 2017-02-05 | 12:00 | 16:00 |  |  | Signed PIA and NDA forms and got familiar with Kairos SDK and try to run their tutorials. The tutorials were not working | 4:00
| Monday | 2017-02-06 | 12:00 | 16:00 |  |  | Learned how to use Mingle, and Created some user stories. Kairos received PIA and NDA forms and added our Github accounts to Kairos repository | 4:00
| Tuesday | 2017-02-07 | 12:00 | 16:00 |  |  | Met with Neil on hangouts. Tried loading their C++ SDK onto Android Studio but did not work | 4:00
| Wednesday | 2017-02-08 | 12:00 | 16:00 |  |  | Met with Neil on hangouts. Discussed more issues that were going on with loading the library | 4:00
| Thusday | 2017-02-09 | 13:00 | 16:00 |  |  | Tried building their entire library manually but it did not work | 3:00
| Friday | 2017-02-10 | 13:00 | 18:00 |  |  | Met with Neil on hangouts. Tried building the library again but would not work. Neil said he will be working on the project with us that for now he is going to fix some things and told us to do alot of research and learn how to use JNI. We will meet with Neil on hangouts again on Wednesday. | 5:00
3 | 6 | [6 empty] | 0:00
| Saturday | 2017-02-11 | [5 empty] | 0:00
| Sunday | 2017-02-12 | [5 empty] | 0:00
| Monday | 2017-02-13 | 20:00 | 24:00 |  |  | Research JSON and GeoJSON Working with traffic simulator team | 4:00
| Tuesday | 2017-02-14 | 14:00 | 18:00 |  |  | Do usefull research on JSON and Geo Json for Traffic Simulator | 4:00
| Wednesday | 2017-02-15 | 14:00 | 18:00 |  |  | Research leaflet and Mapzen | 4:00
| Thusday | 2017-02-16 | 13:00 | 17:00 |  |  | Research leaftlet | 4:00
| Friday | 2017-02-17 | 14:00 | 18:00 |  |  | Figure out how leaflet uses GeoJson then get started on Microsoft AirSim | 4:00
| 7 | [6 empty] | 0:00
| Saturday | 2017-02-18 | [5 empty] | 0:00
| Sunday | 2017-02-19 | [5 empty] | 0:00
| Monday | 2017-02-20 | 14:00 | 18:00 |  |  | Researched on Microsoft AirSim and installed the game engine needed for it, Also downloaded the source code and followed the tutorial up to compilation part. Compile AirSim C++ code from bash command prompt | 4:00
| Tuesday | 2017-02-21 | 14:00 | 18:00 |  |  | Compiled C++ code for AirSim. Now AirSim is running and we see the drone on the map Connect ps4 controller to fly the drone, Ps4 controller is not being recognised by AirSim | 4:00
| Wednesday | 2017-02-22 | 14:00 | 18:00 |  |  | Need to install and compile PX4 software inloop simulator | 4:00
| Thusday | 2017-02-23 | 14:00 | 18:00 |  |  | Keep trying with ps4 controller | 4:00
| Friday | 2017-02-24 | 14:00 | 18:00 |  |  | Try with xbox controller, Mohsen is now switching us to work on News Platform | 4:00
4 | 8 | [6 empty] | 0:00
| Saturday | 2017-02-25 | [5 empty] | 0:00
| Sunday | 2017-02-26 | [5 empty] | 0:00
| Monday | 2017-02-27 | 16:30 | 21:00 |  |  | Planning the system design of News Platform. Start implementing user stories and set up the database. | 4:30
| Tuesday | 2017-02-28 | 14:00 | 18:00 |  |  | Research API sources to get latest news from | 4:00
| Wednesday | 2017-03-01 | 15:00 | 19:00 |  |  | Found Bing News API and Google News RSS Feeds | 4:00
| Thusday | 2017-03-02 | 12:00 | 16:00 |  |  | Develop and algorithm to keep the news updated in our database | 4:00
| Friday | 2017-03-03 | 15:00 | 19:00 |  |  | Algorithm for updating the database has been implemented. Web server will keep the database updated every hour. Thoroughly test the updating algorithm. Make sure data is being updated in database | 4:00
| 9 | [6 empty] | 0:00
| Saturday | 2017-03-04 | [5 empty] | 0:00
| Sunday | 2017-03-05 | [5 empty] | 0:00
| Monday | 2017-03-06 | 14:00 | 18:00 |  |  | Design an algorithm to be able to differentiate news being fetched from API sources and to not store similar news in database | 4:00
| Tuesday | 2017-03-07 | 14:00 | 18:00 |  |  | Test this algorithm above | 4:00
| Wednesday | 2017-03-08 | 16:00 | 20:00 |  |  | Filter out the data that we receive from the source API. The date published must be converted to the local time. If data does not come with an image fetch random images for Bing API based on the web servers News key word | 4:00
| Thusday | 2017-03-09 | 15:00 | 19:00 |  |  | Filter out Google News RSS Feeds Data | 4:00
| Friday | 2017-03-10 | 13:00 | 17:00 |  |  | Developed a regular expression algorithm for cleaning out the html tags from the Google News data. Make the application Mobile Responsive | 4:00
5 | 10 | [6 empty] | 0:00
| Saturday | 2017-03-11 | 14:00 | 18:00 |  |  | Give classes and ids to html elements such that we can have a responsive.css stylesheets where we can set up css values for classes and ids of html elements based on screen sizes. | 4:00
| Sunday | 2017-03-12 | 12:00 | 16:00 |  |  | Working on mobile responsive design | 4:00
| Monday | 2017-03-13 | 12:00 | 16:00 |  |  | Still working on responsive.css file for a mobile responsive application | 4:00
| Tuesday | 2017-03-14 | 15:00 | 19:00 |  |  | News Platform has to be set up as a platform so we must make it such that we can switch the key word on the web server and all the news displayed will be based on that keyword. | 4:00
| Wednesday | 2017-03-15 | 13:00 | 16:00 |  |  | Our controller methods in our web server must take in as parameters the News Key Word. | 3:00
| Thusday | 2017-03-16 | [5 empty] | 0:00
| Friday | 2017-03-17 | [5 empty] | 0:00
| 11 | [6 empty] | 0:00
| Saturday | 2017-03-18 | [5 empty] | 0:00
| Sunday | 2017-03-19 | [5 empty] | 0:00
| Monday | 2017-03-20 | 14:00 | 18:00 |  |  | Fixed all titles so they are based on the web servers News Key Word. Test out the entire application for different news topics | 4:00
| Tuesday | 2017-03-21 | 14:00 | 18:00 |  |  | Research how to use youtube API for latest video search. | 4:00
| Wednesday | 2017-03-22 | 14:00 | 18:00 |  |  | Obtained youtube API key so we can make requests to the youtube API. Set up the web server to make requests to youtube API every hour. | 4:00
| Thusday | 2017-03-23 | 14:00 | 18:00 |  |  | Set up angular script to make request to our web API for youtube videos. Filter out youtube videos data. Video link must set up as youtube.com/embed/<video-id>. Now video is displayed | 4:00
| Friday | 2017-03-24 | 14:00 | 18:00 |  |  | Learn to use twitter API. Got the access token for twitter API through OAuth. Implemented filtering the data and a script for getting the data from web server to web. Display tweets beautifully on the application | 4:00
6 | 12 | [6 empty] | 0:00
| Saturday | 2017-03-25 | 12:00 | 16:00 |  |  | Now when clicking on a news article the source page should open in a new tab so our web site is still opened on another tab | 4:00
| Sunday | 2017-03-26 | 14:00 | 18:00 |  |  | News, videos, and twitter posts must be in 3 separate columns so they are displayed nicely | 4:00
| Monday | 2017-03-27 | 14:00 | 18:00 |  |  | Learned the bootstrap grid system and it was actually very easy to use and was able to set up everything correctly in 3 separate columns. Develop an algorithm to have a google-like pagination for surfing through the news. | 4:00
| Tuesday | 2017-03-28 | 12:00 | 16:00 |  |  | Still working on the pagination. Pagination will be done by next scrum meeting | 4:00
| Wednesday | 2017-03-29 | 12:00 | 16:00 |  |  | Pagination has been finished. Finish up some more design things the product owner wants | 4:00
| Thusday | 2017-03-30 | [5 empty] | 0:00
| Friday | 2017-03-31 | [5 empty] | 0:00
13
| Saturday | 2017-04-01
| Sunday | 2017-04-02
| Monday | 2017-04-03 | 12:00 | 16:00 |  |  | Work on web design
| Tuesday | 2017-04-04 | 14:00 | 18:00 |  |  | Work on web design
| Wednesday | 2017-04-05 | 12:00 | 16:00 |  |  | No more requirements are needed to be implemented. Now sprint 6 is coming to an end so working on small details to finalize the product
| Thusday | 2017-04-06 | 16:00 | 20:00 |  |  | Doing more testing to finalize the product
| Friday | 2017-04-07 | 16:00 | 20:00 |  |  | The product is finished. Did some final testing
7 | 13 | [6 empty] | 0:00
| Saturday | 2017-04-08 | [5 empty] | 0:00
| Sunday | 2017-04-09 | [5 empty] | 0:00
| Monday | 2017-04-10 | 14:00 | 18:00 |  |  | Wrap up. Made sure product owner is happy with final release. Create a slide presentation | 4:00
| Tuesday | 2017-04-11 | 13:00 | 17:00 |  |  | Work on my poster. Work on final documentation | 4:00
| Wednesday | 2017-04-12 | 14:00 | 18:00 |  |  | Work on my poster. Work on final documentation | 4:00
| Thusday | 2017-04-13 | 16:00 | 20:00 |  |  | Work on my poster. Work on final documentation | 4:00
| Friday | 2017-04-14 | 13:00 |  |  |  | Double check presentation, document, and poster | -0.54167
14
| Saturday | 2017-04-15
| Sunday | 2017-04-16
| Monday | 2017-04-17 | 13:00 | 17:00 |  |  | Double check presentation, document, and poster
| Tuesday | 2017-04-18 | 14:00 | 18:00 |  |  | Submit poster online and work on documentation
| Wednesday | 2017-04-19 | 16:00 | 20:00 |  |  | Started working on the videos
| Thusday | 2017-04-20 | 14:00 | 18:00 |  |  | Work on final documentation
| Friday | 2017-04-21 | 16:00 | 20:00 |  |  | Work on videos and final documentation
Formulas:
Date = [Date, row above]+1

## Alejandro Ferragut
Sprint # | Day of Week | Date | Check In | Check Out | Lunch In | Lunch Out | Short description of your work | Daily Hours | Weekly Hours | Overtime Hours | Approval
0 | 1
| Saturday | 2017-01-07 | [5 empty] | 0:00
| Sunday | 2017-01-08 | [5 empty] | 0:00
| Monday | 2017-01-09 | 12:00 | 17:00 |  |  | Watch tutorial Videos | 5:00
| Tuesday | 2017-01-10 | 12:00 | 17:00 |  |  | Watch tutorial Videos | 5:00
| Wednesday | 2017-01-11 | 12:00 | 17:00 |  |  | Learn about Scrum and how to use Mingle | 5:00
| Thusday | 2017-01-12 | 12:00 | 17:00 |  |  | Understand Github and Version Control | 5:00
| Friday | 2017-01-13 | [5 empty] | 0:00
1 | 2 | [6 empty] | 0:00
| Saturday | 2017-01-14 | [5 empty] | 0:00
| Sunday | 2017-01-15 | [5 empty] | 0:00
| Monday | 2017-01-16 | 12:00 | 16:00 |  |  | Review Software Engineering and Testing Concepts | 4:00
| Tuesday | 2017-01-17 | 12:00 | 16:00 |  |  | Meet with Brian and do research about API and SDK concepts | 4:00
| Wednesday | 2017-01-18 | 12:00 | 16:00 |  |  | Research about the company's API and SDK | 4:00
| Thusday | 2017-01-19 | 12:00 | 16:00 |  |  | Learn about Kairos SDK | 4:00
| Friday | 2017-01-20 | 12:00 | 16:00 |  |  | Learn about Kairos SDK | 4:00
| 3 | [6 empty] | 0:00
| Saturday | 2017-01-21 | [5 empty] | 0:00
| Sunday | 2017-01-22 | [5 empty] | 0:00
| Monday | 2017-01-23 | 14:00 | 18:00 |  |  | Do comprehensive research on SDK and API creation | 4:00
| Tuesday | 2017-01-24 | 14:00 | 18:00 |  |  | Do comprehensive research on SDK and API creation | 4:00
| Wednesday | 2017-01-25 | 14:00 | 18:00 |  |  | Work on SDK and API Report | 4:00
| Thusday | 2017-01-26 | 14:00 | 20:00 |  |  | Work on SDK and API report. Provide simple samples, languages, services, and step by step process . Research android NDK | 6:00
| Friday | 2017-01-27 | 14:00 | 18:00 |  |  | Met with Brian and the leading engineer Neil on hangouts to talk about the project. Also worked on SDK and API report. | 4:00
2 | 4 | [6 empty] | 0:00
| Saturday | 2017-01-28 | 12:00 | 16:00 |  |  | Run C++ code examples on Android Studio using JNI | 4:00
| Sunday | 2017-01-29 | 12:00 | 16:00 |  |  | Signed PIA and NDA forms and got familiar with Kairos SDK and try to run their tutorials. The tutorials were not working | 4:00
| Monday | 2017-01-30 | 12:00 | 16:00 |  |  | Learned how to use Mingle, and Created some user stories. Kairos received PIA and NDA forms and added our Github accounts to Kairos repository | 4:00
| Tuesday | 2017-01-31 | 12:00 | 16:00 |  |  | Met with Neil on hangouts. Tried loading their C++ SDK onto Android Studio but did not work | 4:00
| Wednesday | 2017-02-01 | 12:00 | 16:00 |  |  | Met with Neil on hangouts. Discussed more issues that were going on with loading the library | 4:00
| Thusday | 2017-02-02 | 13:00 | 16:00 |  |  | Tried building their entire library manually but it did not work | 3:00
| Friday | 2017-02-03 | 13:00 | 18:00 |  |  | Met with Neil on hangouts. Tried building the library again but would not work. Neil said he will be working on the project with us that for now he is going to fix some things and told us to do alot of research and learn how to use JNI. We will meet with Neil on hangouts again on Wednesday. | 5:00
| 5 | [6 empty] | 0:00
| Saturday | 2017-02-04 | [5 empty] | 0:00
| Sunday | 2017-02-05 | [5 empty] | 0:00
| Monday | 2017-02-06 | 20:00 | 24:00 |  |  | Research about JNI | 4:00
| Tuesday | 2017-02-07 | 14:00 | 18:00 |  |  | Met on hangouts with Neil, he said he will build the native library because Chris and I do not know how to do it and we have tried for the past month. Neil says for now learn JNI and build a skeleton | 4:00
| Wednesday | 2017-02-08 | 14:00 | 18:00 |  |  | Research more about JNI | 4:00
| Thusday | 2017-02-09 | [5 empty] | 0:00
| Friday | 2017-02-10 | 14:00 | 18:00 |  |  | Met on hangouts with Neil, he will have a working library by tuesday while we research and work on JNI | 4:00
3 | 6 | [6 empty] | 0:00
| Saturday | 2017-02-11 | 13:00 | 18:00 |  |  | Research on JNI, trying to build example project where we return a C++ class to Java | 5:00
| Sunday | 2017-02-12 | 20:00 | 23:59 |  |  | JNI examples, trying to instantiate a sample C++ class. We are able to call methods from c++ in java but lose the object | 3:59
| Monday | 2017-02-13 | 15:00 | 20:00 |  |  | JNI work - Chris was able to keep global pointer. I have been trying to instantiate class from C++ JNI. | 5:00
| Tuesday | 2017-02-14 | [5 empty] | 0:00
| Wednesday | 2017-02-15 | 14:00 | 19:00 |  |  | Work on documentation, keep learning JNI. | 5:00
| Thusday | 2017-02-16 | [5 empty] | 0:00
| Friday | 2017-02-17 | [5 empty] | 0:00
| 7 | [6 empty] | 0:00
| Saturday | 2017-02-18 | 13:00 | 18:00 |  |  | Work on another version of JNI (without pointers) | 5:00
| Sunday | 2017-02-19 | [5 empty] | 0:00
| Monday | 2017-02-20 | 13:00 | 18:00 |  |  | Work on another version of JNI (without pointers) 2 | 5:00
| Tuesday | 2017-02-21 | 19:00 | 23:00 |  |  | Work on another version of JNI (without pointers) 3 | 4:00
| Wednesday | 2017-02-22 | [5 empty] | 0:00
| Thusday | 2017-02-23 | 14:00 | 18:00 |  |  | Continued working on sample JNI | 4:00
| Friday | 2017-02-24 | 14:00 | 16:00 |  |  | Met with Neil , he said he will have the library ready by next Friday | 2:00
4 | 8 | [6 empty] | 0:00
| Saturday | 2017-02-25 | [5 empty] | 0:00
| Sunday | 2017-02-26 | [5 empty] | 0:00
| Monday | 2017-02-27 | 19:00 | 23:40 |  |  | Completed example of JNI without pointers by returning an array with the info. | 4:40
| Tuesday | 2017-02-28 | 14:00 | 18:00 |  |  | Work on documentation and other possible JNI solutions | 4:00
| Wednesday | 2017-03-01 | 14:00 | 18:00 |  |  | Research on JSON and links from Traffic simulator | 4:00
| Thusday | 2017-03-02 | 14:30 | 19:30 |  |  | Meeting with Traffic simulator team. Did research on Mapzen, leaftlet, and geoJSON for traffic simulator | 5:00
| Friday | 2017-03-03 | 14:00 | 18:00 |  |  | Research on AirSim from Microsoft | 4:00
| 9 | [6 empty] | 0:00
| Saturday | 2017-03-04 | [5 empty] | 0:00
| Sunday | 2017-03-05 | [5 empty] | 0:00
| Monday | 2017-03-06 | 18:00 | 23:00 |  |  | Work with Chris on researching and setting up AirSim | 5:00
| Tuesday | 2017-03-07 | [5 empty] | 0:00
| Wednesday | 2017-03-08 | 14:00 | 20:00 |  |  | Try to setup Xbox 360 controller with AirSim. Research on API's | 6:00
| Thusday | 2017-03-09 | 14:00 | 20:00 |  |  | Setup Udacity self driving simulator on unity. Research on the dependencies to get the autonomous part working. | 6:00
| Friday | 2017-03-10 | 14:00 | 18:00 |  |  | Documentation , research on API's , Jquery and Ajax | 4:00
5 | 10 | [6 empty] | 0:00
| Saturday | 2017-03-11 | [5 empty] | 0:00
| Sunday | 2017-03-12 | 14:00 | 18:00 |  |  | Research on other API's. Setup google search API and newsapi.org , push to github | 4:00
| Monday | 2017-03-13 | 14:00 | 18:00 |  |  | Research Google Alerts, Microsoft Bing News Search, and WebHose | 4:00
| Tuesday | 2017-03-14 | 14:00 | 18:00 |  |  | Get Google Alerts and Microsoft Bing News Search data making http calls to APIs | 4:00
| Wednesday | 2017-03-15 | 14:00 | 18:00 |  |  | Work on User Interface, bootstrap and angularjs research | 4:00
| Thusday | 2017-03-16 | 14:00 | 18:00 |  |  | Work on User Interface, bootstrap and angularjs research | 4:00
| Friday | 2017-03-17 | [5 empty] | 0:00
| 11 | [6 empty] | 0:00
| Saturday | 2017-03-18 | [5 empty] | 0:00
| Sunday | 2017-03-19 | [5 empty] | 0:00
| Monday | 2017-03-20 | [5 empty] | 0:00
| Tuesday | 2017-03-21 | 14:00 | 18:00 |  |  | Research on bootstrap and angularJS | 4:00
| Wednesday | 2017-03-22 | 14:00 | 18:00 |  |  | Research on bootstrap and angularJS | 4:00
| Thusday | 2017-03-23 | 14:00 | 18:00 |  |  | Work on the UI | 4:00
| Friday | 2017-03-24 | 14:00 | 18:00 |  |  | Meet with Chris, Look for a boostrap template to use, and research | 4:00
6 | 12 | [6 empty] | 0:00
| Saturday | 2017-03-25 | [5 empty] | 0:00
| Sunday | 2017-03-26 | 12:00 | 16:00 |  |  | Meet with Chris, work on backend. Found/purchase template. Familiarize with new template | 4:00
| Monday | 2017-03-27 | 17:00 | 21:00 |  |  | Meet with Chris. More work on backend: c# part and search query. Modify Template | 4:00
| Tuesday | 2017-03-28 | [5 empty] | 0:00
| Wednesday | 2017-03-29 | 13:00 | 19:00 |  |  | Meet with Chris. Work on FrontEnd, start feature document on Search feature | 6:00
| Thusday | 2017-03-30 | [5 empty] | 0:00
| Friday | 2017-03-31 | 14:00 | 18:00 |  |  | Research on Twitter, instagram and facebook API's | 4:00
| 13 | [6 empty] | 0:00
| Saturday | 2017-04-01 | [5 empty] | 0:00
| Sunday | 2017-04-02 | [5 empty] | 0:00
| Monday | 2017-04-03 | 18:00 | 23:00 |  |  | Meet with Chris. On Graphical Interface | 5:00
| Tuesday | 2017-04-04 | 14:00 | 18:00 |  |  | Continue work | 4:00
| Wednesday | 2017-04-05 | 14:00 | 19:00 |  |  | Work on frontend: html & angular. improve readability. | 5:00
| Thusday | 2017-04-06 | 14:00 | 17:00 |  |  | Documentation | 3:00
| Friday | 2017-04-07 | [5 empty] | 0:00
7 | 14 | [6 empty] | 0:00
| Saturday | 2017-04-08 | [5 empty] | 0:00
| Sunday | 2017-04-09 | [5 empty] | 0:00
| Monday | 2017-04-10 | 14:00 | 18:00 |  |  | Work on website toolbar, hidding latest news after search. | 4:00
| Tuesday | 2017-04-11 | 14:00 | 19:00 |  |  | Fix pagination & work on documentation | 5:00
| Wednesday | 2017-04-12 | 14:00 | 18:00 |  |  | documentation | 4:00
| Thusday | 2017-04-13 | [5 empty] | 0:00
| Friday | 2017-04-14 | 14:00 | 18:00 |  |  | poster | 4:00
| 15 | [6 empty] | 0:00
| Saturday | 2017-04-15 | 14:00 | 18:00 |  |  | poster/ documentation | 4:00
| Sunday | 2017-04-16 | 14:00 | 18:00 |  |  | documentation | 4:00
| Monday | 2017-04-17 | 14:00 | 19:00 |  |  | documentation / powerpoint | 5:00
| Tuesday | 2017-04-18 | [5 empty] | 0:00
| Wednesday | 2017-04-19 | 14:00 | 19:00 |  |  | documentation / videos | 5:00
| Thusday | 2017-04-20 | 13:00 | 20:00 |  |  | documentation / videos | 7:00
| Friday | 2017-04-21 | [5 empty] | 0:00
Formulas:
Date = [Date, row above]+1