## Daniel
Sprint # | Day of Week | Date | Check In | Check Out | Lunch In | Lunch Out | Short description of your work | Daily Hours | Weekly Hours | Overtime Hours | Approval
0 | 1
| Saturday | 2016-05-14 | [5 empty] | 0:00:00
| Sunday | 5/15/2016 | [5 empty] | 0:00:00
| Monday | 5/16/2016 | 19:45 | 21:45 |  |  | Learn about senior project | 2:00:00
| Tuesday | 5/17/2016 | 13:00 | 18:00 |  |  | Watch Videos | 5:00:00
| Wednesday | 5/18/2016 | 13:00 | 22:00 | 14:30 | 16:30 | Learn Angular JS | 7:00:00
| Thusday | 5/19/2016 | 15:00 | 20:00 |  |  | Learn Node JS, Express, and MongoDB | 5:00:00
| Friday | 5/20/2016 | 13:00 | 19:00 |  |  | Learn Git and setup MEAN stack | 6:00:00 | 25 | 0
1 | 2 | [6 empty] | 0:00:00
| Saturday | 5/21/2016 | [5 empty] | 0:00:00
| Sunday | 5/22/2016 | [5 empty] | 0:00:00
| Monday | 5/23/2016 | 22:00 | 23:00 |  |  | Make first commit of old code in GIT. | 1:00:00
| Tuesday | 5/24/2016 | 13:00 | 21:00 |  |  | Setup mingle account. | 8:00:00
| Wednesday | 5/25/2016 | 18:00 | 22:00 |  |  | Make feasibility report and make user storys for first sprint. | 4:00:00
| Thusday | 5/26/2016 | 13:00 | 20:30 | 17:00 | 18:30 | Add a user story to sprint 1. Start working on user story document. Met with moshen | 6:00:00
| Friday | 5/27/2016 | 10:00 | 15:30 | 12:00 | 12:30 | Get approval for user story and work on user story document and research about user story. | 10:00:00 | 25 | 4
| 3 | [6 empty] | 0:00:00
| Saturday | 5/28/2016 | [5 empty] | 0:00:00
| Sunday | 5/29/2016 | [5 empty] | 0:00:00
| Monday | 5/30/2016 | [5 empty] | 0:00:00
| Tuesday | 5/31/2016 | 9:00 | 15:30 | 12:00 | 12:30 | Complete user story #955 | 6:00:00
| Wednesday | 6/1/2016 | 10:30 | 20:30 | 14:30 | 16:30 | Work on related task #965. | 8:00:00
| Thusday | 6/2/2016 | 10:30 | 22:00 | 12:30 | 13:00 | Help Michael with his task, manage git repo, etc. | 11:00:00
| Friday | 6/3/2016 | [5 empty] | 0:00:00 | 25 | 0
2 | 4 | [6 empty] | 0:00:00
| Saturday | 6/4/2016 | [5 empty] | 0:00:00
| Sunday | 6/5/2016 | [5 empty] | 0:00:00
| Monday | 6/6/2016 | 10:00 | 18:00 | 12:00 | 12:30 | Prepare for bi-weekly meeting. | 7:30:00
| Tuesday | 6/7/2016 | 11:00 | 18:00 | 12:00 | 12:30 | Prepare stories for sprint 2. Start feature document. | 6:30:00
| Wednesday | 6/8/2016 | 11:00 | 17:30 | 12:00 | 12:30 | Finish user story #970. | 6:00:00
| Thusday | 6/9/2016 | 16:30 | 18:30 |  |  | Start next user story. | 2:00:00
| Friday | 6/10/2016 | 15:30 | 18:30 |  |  | Continue on current user story. | 3:00:00
| 5 | [6 empty] | 0:00:00 | 25 | 0
| Saturday | 6/11/2016 | [5 empty] | 0:00:00
| Sunday | 6/12/2016 | [5 empty] | 0:00:00
| Monday | 6/13/2016 | 12:00 | 17:00 |  |  | Finish user story #981 | 5:00:00
| Tuesday | 6/14/2016 | 12:00 | 17:00 |  |  | Fix bugs. | 5:00:00
| Wednesday | 6/15/2016 | 8:00 | 23:00 |  |  | Fix bugs. | 15:00:00
| Thusday | 6/16/2016 |  |  |  |  | Excused Absence | 0:00:00
| Friday | 6/17/2016 |  |  |  |  | Excused Absence | 0:00:00 | 25
3 | 6 | [6 empty] | 0:00:00
| Saturday | 6/18/2016 | [5 empty] | 0:00:00
| Sunday | 6/19/2016 | [5 empty] | 0:00:00
| Monday | 6/20/2016 | 9:00 | 15:00 | 12:00 | 12:30 | Prepare live server. Prepare for end of sprint. | 5:30:00
| Tuesday | 6/21/2016 | 9:00 | 15:00 | 12:00 | 12:30 | Prepare for third sprint. | 5:30:00
| Wednesday | 6/22/2016 | 9:00 | 15:00 | 12:00 | 12:30 | Fix bugs. | 5:30:00
| Thusday | 6/23/2016 | 9:00 | 15:00 | 12:00 | 12:30 | Fix bugs. | 5:30:00
| Friday | 6/24/2016 | 9:00 | 15:00 | 12:00 | 12:30 | Fix bugs. | 5:30:00
| 7 | [6 empty] | 0:00:00
| Saturday | 6/25/2016 | [5 empty] | 0:00:00
| Sunday | 6/26/2016 | [5 empty] | 3:00:00
| Monday | 6/27/2016 | 9:00 | 15:00 | 12:00 | 12:30 | Fix bugs. | 5:30:00
| Tuesday | 6/28/2016 | 9:00 | 15:00 | 12:00 | 12:30 | Fix bugs. | 5:30:00
| Wednesday | 6/29/2016 | 9:00 | 15:00 | 12:00 | 12:30 | Fix bugs. | 5:30:00
| Thusday | 6/30/2016 | 9:00 | 15:00 | 12:00 | 12:30 | Fix bugs. | 5:30:00
| Friday | 7/1/2016 | 9:00 | 15:00 | 12:00 | 12:30 | Fix bugs. | 5:30:00 | 25
4 | 8 | [6 empty] | 0:00:00
| Saturday | 7/2/2016 | [5 empty] | 0:00:00
| Sunday | 7/3/2016 | [5 empty] | 0:00:00
| Monday | 7/4/2016 | 9:00 | 15:00 | 12:00 | 12:30 | Prepare for fourth sprint. | 5:30:00
| Tuesday | 7/5/2016 | 9:00 | 15:00 | 12:00 | 12:30 | Fix bugs and work on user stories. | 5:30:00
| Wednesday | 7/6/2016 | 9:00 | 15:00 | 12:00 | 12:30 | Fix bugs and work on user stories. | 5:30:00
| Thusday | 7/7/2016 | 9:00 | 15:00 | 12:00 | 12:30 | Fix bugs and work on user stories. | 5:30:00
| Friday | 7/8/2016 | 9:00 | 15:00 | 12:00 | 12:30 | Fix bugs and work on user stories. | 5:30:00 | 25
| 9 | [6 empty] | 0:00:00
| Saturday | 7/9/2016 | [5 empty] | 0:00:00
| Sunday | 7/10/2016 | [5 empty] | 0:00:00
| Monday | 7/11/2016 | 9:00 | 15:00 | 12:00 | 12:30 | Fix bugs and work on user stories. | 5:30:00
| Tuesday | 7/12/2016 | 9:00 | 15:00 | 12:00 | 12:30 | Fix bugs and work on user stories. | 5:30:00
| Wednesday | 7/13/2016 | 9:00 | 15:00 | 12:00 | 12:30 | Fix bugs and work on user stories. | 5:30:00
| Thusday | 7/14/2016 | 9:00 | 15:00 | 12:00 | 12:30 | Fix bugs and work on user stories. | 5:30:00
| Friday | 7/15/2016 | 9:00 | 15:00 | 12:00 | 12:30 | Fix bugs and work on user stories. | 5:30:00 | 25
5 | 10 | [6 empty] | 0:00:00
| Saturday | 7/16/2016 | [5 empty] | 0:00:00
| Sunday | 7/17/2016 | [5 empty] | 0:00:00
| Monday | 7/18/2016 | 9:00 | 15:00 | 12:00 | 12:30 | Prepare for fifth sprint. | 5:30:00
| Tuesday | 7/19/2016 | 9:00 | 15:00 | 12:00 | 12:30 | Fix bugs and work on user stories. | 5:30:00
| Wednesday | 7/20/2016 | 9:00 | 15:00 | 12:00 | 12:30 | Fix bugs and work on user stories. | 5:30:00
| Thusday | 7/21/2016 | 9:00 | 15:00 | 12:00 | 12:30 | Fix bugs and work on user stories. | 5:30:00
| Friday | 7/22/2016 | 9:00 | 15:00 | 12:00 | 12:30 | Fix bugs and work on user stories. | 5:30:00 | 25
| 11 | [6 empty] | 0:00:00
| Saturday | 7/23/2016 | [5 empty] | 0:00:00
| Sunday | 7/24/2016 | [5 empty] | 0:00:00
| Monday | 7/25/2016 | 9:00 | 15:00 | 12:00 | 12:30 | Fix bugs and work on user stories. | 5:30:00
| Tuesday | 7/26/2016 | 9:00 | 15:00 | 12:00 | 12:30 | Fix bugs and work on user stories. | 5:30:00
| Wednesday | 7/27/2016 | 9:00 | 15:00 | 12:00 | 12:30 | Fix bugs and work on user stories. | 5:30:00
| Thusday | 7/28/2016 | 9:00 | 15:00 | 12:00 | 12:30 | Fix bugs and work on user stories. | 5:30:00
| Friday | 7/29/2016 | 9:00 | 15:00 | 12:00 | 12:30 | Fix bugs and work on user stories. | 5:30:00 | 25
6 | 12 | [6 empty] | 0:00:00
| Saturday | 7/30/2016 | [5 empty] | 0:00:00
| Sunday | 7/31/2016 | [5 empty] | 0:00:00
| Monday | 8/1/2016 | 9:00 | 15:00 | 12:00 | 12:30 | Work on poster. | 5:30:00
| Tuesday | 8/2/2016 | 9:00 | 15:00 | 12:00 | 12:30 | Work on videos. | 5:30:00
| Wednesday | 8/3/2016 | 9:00 | 15:00 | 12:00 | 12:30 | Work on videos. | 5:30:00
| Thusday | 8/4/2016 | 9:00 | 15:00 | 12:00 | 12:30 | Work on final deliverables. | 5:30:00
| Friday | 8/5/2016 | 9:00 | 15:00 | 12:00 | 12:30 | Present and fill out survey. | 5:30:00 | 25

## Vladan
Sprint # | Day of Week | Date | Check In | Check Out | Lunch In | Lunch Out | Short description of your work | Daily Hours | Weekly Hours | Overtime Hours | Approval
0 | 1
| Saturday | 2016-05-14 | [5 empty] | 0:00:00
| Sunday | 5/15/2016 | [5 empty] | 0:00:00
| Monday | 5/16/2016 | 19:45 | 21:45 |  |  | Learn about senior project | 2:00:00
| Tuesday | 5/17/2016 | 13:00 | 18:00 |  |  | Watch Videos | 5:00:00
| Wednesday | 5/18/2016 | 13:00 | 22:00 | 14:30 | 16:30 | Learn Angular JS | 7:00:00
| Thusday | 5/19/2016 | 15:00 | 20:00 |  |  | Learn Node JS, Express, and MongoDB | 5:00:00
| Friday | 5/20/2016 | 13:00 | 19:00 |  |  | Learn Git and setup MEAN stack | 6:00:00
1 | 2 | [6 empty] | 0:00:00
| Saturday | 5/21/2016 | [5 empty] | 0:00:00
| Sunday | 5/22/2016 | [5 empty] | 0:00:00
| Monday | 5/23/2016 | 22:00 | 23:00 |  |  | Make first commit of old code in GIT. | 1:00:00
| Tuesday | 5/24/2016 | 13:00 | 20:30 | 14:00 | 15:30 | Setup mingle account. | 6:00:00
| Wednesday | 5/25/2016 | 14:30 | 21:30 | 17:30 | 18:30 | Wrote feasability report. Google API Research. Created Google API Demo in VIP 3.0 | 6:00:00
| Thusday | 5/26/2016 | 13:00 | 23:30 | 17:00 | 21:00 | Met with Mentor (Mr. Mohsen) on Skype. Created 4 User Stories. Began Sprint 1. | 6:30:00
| Friday | 5/27/2016 | 16:00 | 23:30 | 17:00 | 19:00 | Performed audit of existing features. Revised Story. Created 3 tasks for Story. | 5:30:00
| 3 | [6 empty] | 0:00:00
| Saturday | 5/28/2016 | [5 empty] | 0:00:00
| Sunday | 5/29/2016 | 19:00 | 21:00 |  |  | Switched priority to User Story #956. Traced the source of the Registration error bug. | 2:00:00
| Monday | 5/30/2016 | 14:00 | 16:00 |  |  | Fixed User Registration bug. Fixed email verification bug. Requested vip.fiu.edu access. | 2:00:00
| Tuesday | 5/31/2016 | 9:30 | 20:30 | 13:30 | 17:30 | Began working on documentation for Story #956. Helped team fix bugs. Added new tasks. | 7:00:00
| Wednesday | 6/1/2016 | 15:00 | 21:00 | 16:00 | 17:00 | Finished task #963 and task #964. Fixed another Registration bug. Worked on documentation. | 5:00:00
| Thusday | 6/2/2016 | 15:00 | 23:00 | 17:00 | 18:30 | Finished more sections of Feature Document. Began Unit Testing for User Story #956. | 6:30:00
| Friday | 6/3/2016 | 17:00 | 20:00 |  |  | Deployed fixes to live server so Mr. Mohsen can test. | 3:00:00
2 | 4 | [6 empty] | 0:00:00
| Saturday | 6/4/2016 | [5 empty] | 0:00:00
| Sunday | 6/5/2016 | 14:00 | 20:00 |  |  | Fixes on vip.fiu.edu server. | 6:00:00
| Monday | 6/6/2016 | 14:00 | 19:00 |  |  | Meeting with Mr. Mohsen. Updated User Stories in Mingle. Began documentation. | 5:00:00
| Tuesday | 6/7/2016 | 11:00 | 20:00 | 13:00 | 15:00 | Worked on documentation. Revised stories and got them approved. | 7:00:00
| Wednesday | 6/8/2016 | 17:00 | 21:30 |  |  | Almost finished with coding/documentation for User Story #973. Clarified question with PI. | 4:30:00
| Thusday | 6/9/2016 | 14:00 | 19:30 | 17:00 | 18:00 | Switched User Stories upon Mr. Mohsen's request to Login. I completed the updates for Login. | 4:30:00
| Friday | 6/10/2016 | [5 empty] | 0:00:00
| 5 | [6 empty] | 0:00:00
| Saturday | 6/11/2016 | [5 empty] | 0:00:00
| Sunday | 6/12/2016 | [5 empty] | 0:00:00
| Monday | 6/13/2016 | 17:00 | 21:30 |  |  | Updated the Login user story to the new specifications. Began working on fixes. | 4:30:00
| Tuesday | 6/14/2016 | 16:00 | 22:00 |  |  | Testing fixes for login, working on documents for user stories. | 6:00:00
| Wednesday | 6/15/2016 | 16:00 | 21:00 |  |  | Spent some time fixing merge conflicts. Updated database schema. | 5:00:00
| Thusday | 6/16/2016 | 15:00 | 20:30 |  |  | Finished user story for the Profile page - had to update userType conditions in code. | 5:30:00
| Friday | 6/17/2016 | 14:00 | 20:00 |  |  | Merged and pushed all of our groups code to server. | 6:00:00
3 | 6 | [6 empty] | 0:00:00
| Saturday | 6/18/2016 | [5 empty] | 0:00:00
| Sunday | 6/19/2016 | [5 empty] | 0:00:00
| Monday | 6/20/2016 | 17:00 | 23:00 | 21:00 | 22:00 | Merged all changes, pushed it to server, and found new bugs to work on. Created user stories. | 5:00:00
| Tuesday | 6/21/2016 | 17:00 | 22:00 |  |  | Created visual guides for Deleting users and Restarting VIP. Approved new user stories. | 5:00:00
| Wednesday | 6/22/2016 | 16:00 | 21:00 |  |  | Began working on documents for the new user stories. | 5:00:00
| Thusday | 6/23/2016 | 15:30 | 20:30 |  |  | Got feedback for the diagrams and revised. Setup the dev server with Michael. | 5:00:00
| Friday | 6/24/2016 | 18:00 | 23:00 |  |  | Edited the accept profile page so that it refreshes after update. And updated the diagrams and feature documents | 5:00:00
| 7 | [6 empty] | 0:00:00
| Saturday | 6/25/2016 | [5 empty] | 0:00:00
| Sunday | 6/26/2016 | [5 empty] | 0:00:00
| Monday | 6/27/2016 | 14:00 | 19:30 |  |  | Helped team with slides for presentation. Did group presentations. | 5:30:00
| Tuesday | 6/28/2016 | 13:00 | 20:00 |  |  | Fixed many bugs with VIP. | 7:00:00
| Wednesday | 6/29/2016 | 13:00 | 19:00 |  |  | Fixed "back" button not working. Now works on apply page/propose project page | 6:00:00
| Thusday | 6/30/2016 | 14:00 | 21:00 |  |  | Helped team fix new issues from meeting and update live server. | 7:00:00
| Friday | 7/1/2016 | 14:00 | 19:00 |  |  | Fixing bugs with team in preparation for final release for users. | 5:00:00
4 | 8 | [6 empty] | 0:00:00
| Saturday | 7/2/2016 | [5 empty] | 0:00:00
| Sunday | 7/3/2016 | [5 empty] | 0:00:00
| Monday | 7/4/2016 | 13:00 | 19:00 |  |  | Audited current features and found new bugs. | 6:00:00
| Tuesday | 7/5/2016 | 13:00 | 20:00 |  |  | Finished documentation, began working on Messaging Feature. | 7:00:00
| Wednesday | 7/6/2016 | 13:00 | 19:00 |  |  | Fixed a bunch of bugs and updated the live server. | 6:00:00
| Thusday | 7/7/2016 | 14:30 | 19:00 |  |  | Worked on documentation for messaging feature. | 4:30:00
| Friday | 7/8/2016 | 14:30 | 19:30 |  |  | Helped Michael with writing the filters for the Administration Panel | 5:00:00
| 9 | [6 empty] | 0:00:00
| Saturday | 7/9/2016 | [5 empty] | 0:00:00
| Sunday | 7/10/2016 | [5 empty] | 0:00:00
| Monday | 7/11/2016 | 9:00 | 15:00 | 12:00 | 12:30 | Fix bugs and work on user stories. | 5:30:00
| Tuesday | 7/12/2016 | 9:00 | 15:00 | 12:00 | 12:30 | Fix bugs and work on user stories. | 5:30:00
| Wednesday | 7/13/2016 | 9:00 | 15:00 | 12:00 | 12:30 | Fix bugs and work on user stories. | 5:30:00
| Thusday | 7/14/2016 | 9:00 | 15:00 | 12:00 | 12:30 | Fix bugs and work on user stories. | 5:30:00
| Friday | 7/15/2016 | 9:00 | 15:00 | 12:00 | 12:30 | Fix bugs and work on user stories. | 5:30:00
5 | 10 | [6 empty] | 0:00:00
| Saturday | 7/16/2016 | [5 empty] | 0:00:00
| Sunday | 7/17/2016 | [5 empty] | 0:00:00
| Monday | 7/18/2016 | 9:00 | 15:00 | 12:00 | 12:30 | Prepare for fifth sprint. | 5:30:00
| Tuesday | 7/19/2016 | 9:00 | 15:00 | 12:00 | 12:30 | Fix bugs and work on user stories. | 5:30:00
| Wednesday | 7/20/2016 | 9:00 | 15:00 | 12:00 | 12:30 | Fix bugs and work on user stories. | 5:30:00
| Thusday | 7/21/2016 | 9:00 | 15:00 | 12:00 | 12:30 | Fix bugs and work on user stories. | 5:30:00
| Friday | 7/22/2016 | 9:00 | 15:00 | 12:00 | 12:30 | Fix bugs and work on user stories. | 5:30:00
| 11 | [6 empty] | 0:00:00
| Saturday | 7/23/2016 | [5 empty] | 0:00:00
| Sunday | 7/24/2016 | [5 empty] | 0:00:00
| Monday | 7/25/2016 | 9:00 | 15:00 | 12:00 | 12:30 | Fix bugs and work on user stories. | 5:30:00
| Tuesday | 7/26/2016 | 9:00 | 15:00 | 12:00 | 12:30 | Fix bugs and work on user stories. | 5:30:00
| Wednesday | 7/27/2016 | 9:00 | 15:00 | 12:00 | 12:30 | Fix bugs and work on user stories. | 5:30:00
| Thusday | 7/28/2016 | 9:00 | 15:00 | 12:00 | 12:30 | Fix bugs and work on user stories. | 5:30:00
| Friday | 7/29/2016 | 9:00 | 15:00 | 12:00 | 12:30 | Fix bugs and work on user stories. | 5:30:00
6 | 12 | [6 empty] | 0:00:00
| Saturday | 7/30/2016 | [5 empty] | 0:00:00
| Sunday | 7/31/2016 | [5 empty] | 0:00:00
| Monday | 8/1/2016 | 9:00 | 15:00 | 12:00 | 12:30 | Work on poster. | 5:30:00
| Tuesday | 8/2/2016 | 9:00 | 15:00 | 12:00 | 12:30 | Work on videos. | 5:30:00
| Wednesday | 8/3/2016 | 9:00 | 15:00 | 12:00 | 12:30 | Work on videos. | 5:30:00
| Thusday | 8/4/2016 | 9:00 | 15:00 | 12:00 | 12:30 | Work on final deliverables. | 5:30:00
| Friday | 8/5/2016 | 9:00 | 15:00 | 12:00 | 12:30 | Present and fill out survey. | 5:30:00

## Michael
Sprint # | Day of Week | Date | Check In | Check Out | Lunch In | Lunch Out | Short description of your work | Daily Hours | Weekly Hours | Overtime Hours | Approval
0 | 1
| Saturday | 2016-05-14 | [5 empty] | 0:00:00
| Sunday | 5/15/2016 | [5 empty] | 0:00:00
| Monday | 5/16/2016 | 19:45 | 21:45 |  |  | Learn about senior project | 2:00:00
| Tuesday | 5/17/2016 | 13:00 | 18:00 |  |  | Watch Videos | 5:00:00
| Wednesday | 5/18/2016 | 13:00 | 22:00 | 14:30 | 16:30 | Learn Angular JS | 7:00:00
| Thusday | 5/19/2016 | 15:00 | 20:00 |  |  | Learn Node JS, Express, and MongoDB | 5:00:00
| Friday | 5/20/2016 | 13:00 | 19:00 |  |  | Learn Git and setup MEAN stack | 6:00:00
1 | 2 | [6 empty] | 0:00:00
| Saturday | 5/21/2016 | [5 empty] | 0:00:00
| Sunday | 5/22/2016 | [5 empty] | 0:00:00
| Monday | 5/23/2016 | 14:00 | 23:00 | 16:00 | 22:00 | Make first commit of old code in GIT. | 3:00:00
| Tuesday | 5/24/2016 | 14:00 | 20:30 | 15:00 | 17:00 | Setup mingle account. | 4:30:00
| Wednesday | 5/25/2016 | 14:00 | 21:30 | 16:00 | 18:00 | Make feasibility report and come up with user storys for first sprint. | 5:30:00
| Thusday | 5/26/2016 | 13:00 | 20:00 | 17:00 | 18:00 | Discuss with team members and mentor about new user stories and choosing a story to work on. | 6:00:00
| Friday | 5/27/2016 | 14:00 | 21:00 | 16:00 | 16:30 | Setup Robomongo, test proposal page on VIP, refine user story and add tasks | 6:30:00
| 3 | [6 empty] | 0:00:00
| Saturday | 5/28/2016 | [5 empty] | 0:00:00
| Sunday | 5/29/2016 | [5 empty] | 0:00:00
| Monday | 5/30/2016 |  |  |  |  | Labor day | 0:00:00
| Tuesday | 5/31/2016 | 14:00 | 20:00 | 15:00 | 16:00 | Added "Links" userstory and working on current userstory | 5:00:00
| Wednesday | 6/1/2016 | 12:00 | 24:00 | 16:00 | 17:30 | created a new route, service, controller, and module for header | 10:29:59
| Thusday | 6/2/2016 | 12:00 | 20:00 | 15:30 | 16:00 | figured out a better way to implement my userstory(thanks to Danny). Deleted what I did yesterday and finished the user story today. | 7:30:00
| Friday | 6/3/2016 | 11:30 | 18:00 | 14:00 | 16:30 | finished the documentation for my user story | 4:00:00
2 | 4 | [6 empty] | 0:00:00
| Saturday | 6/4/2016 | [5 empty] | 0:00:00
| Sunday | 6/5/2016 | [5 empty] | 0:00:00
| Monday | 6/6/2016 | 13:00 | 20:00 | 14:00 | 16:00 | Fixing stuff from last user story, and creating new user stories | 5:00:00
| Tuesday | 6/7/2016 | 14:00 | 19:30 | 15:00 | 15:30 | Add tasks to user story, fix links & bugs from last user story, work on documentation | 5:00:00
| Wednesday | 6/8/2016 | 12:00 | 21:00 | 13:00 | 17:00 | Worked on documentation and working on Review Student applications page | 5:00:00
| Thusday | 6/9/2016 | 14:00 | 21:00 | 16:00 | 18:00 | Working on Review Student applications and Project Proposal | 5:00:00
| Friday | 6/10/2016 | 15:00 | 22:00 |  |  | Finished Apply for project and Project Proposals buttons on Main page, working on the other user stories | 7:00:00
| 5 | [6 empty] | 0:00:00
| Saturday | 6/11/2016 | [5 empty] | 0:00:00
| Sunday | 6/12/2016 | [5 empty] | 0:00:00
| Monday | 6/13/2016 | 14:00 | 20:00 | 15:00 | 16:00 | Working on Review Student Application & Review Project Proposals | 5:00:00
| Tuesday | 6/14/2016 | 12:00 | 20:00 | 18:30 | 19:00 | Finished Review Project Proposals and Working on Review Student Applications | 7:30:00
| Wednesday | 6/15/2016 | 14:00 | 22:00 | 17:00 | 18:30 | Working on Review Student Application | 6:30:00
| Thusday | 6/16/2016 | 13:00 | 23:00 | 16:00 | 18:00 | Finished Review Student Application and fixing git hub merge conflicts and other issues | 8:00:00
| Friday | 6/17/2016 | 14:00 | 16:00 |  |  | Testing Code | 2:00:00
3 | 6 | [6 empty] | 0:00:00
| Saturday | 6/18/2016 | [5 empty] | 0:00:00
| Sunday | 6/19/2016 | [5 empty] | 0:00:00
| Monday | 6/20/2016 | 12:00 | 23:30 | 13:00 | 16:00 | Sprint review and retrospective, Fixing code, and pushing changes to live server with team | 8:30:00
| Tuesday | 6/21/2016 | 13:00 | 21:00 | 15:00 | 17:00 | Monitoring live server, figuring out errors, fixing errors, and creating new user stories for sprint | 6:00:00
| Wednesday | 6/22/2016 | 14:00 | 20:00 | 15:00 | 16:00 | downloaded and installed visio, Working on diagrams, updated sprint view for mingle | 5:00:00
| Thusday | 6/23/2016 | 14:00 | 20:00 | 15:00 | 16:00 | Worked on user story | 5:00:00
| Friday | 6/24/2016 | 14:00 | 20:00 | 15:00 | 16:00 | Fixed buttons for mobile phone and worked on user story | 5:00:00
| 7 | [6 empty] | 0:00:00
| Saturday | 6/25/2016 | [5 empty] | 0:00:00
| Sunday | 6/26/2016 | 18:00 | 22:00 |  |  | worked on slides for presentation | 4:00:00
| Monday | 6/27/2016 | 17:00 | 19:30 |  |  | worked on slides and practiced presenting with group | 2:30:00
| Tuesday | 6/28/2016 | 14:00 | 21:00 | 16:00 | 17:00 | Fix colors for buttons, created schema for log and storing them(history feature user story) | 6:00:00
| Wednesday | 6/29/2016 | 13:00 | 20:00 | 16:00 | 18:00 | create services and controller functions for saving and retrieving log files in review project proposal | 5:00:00
| Thusday | 6/30/2016 | 16:00 | 23:00 | 20:00 | 22:00 | fixed bug on apply and added update rank on apply page for gmail login, added more text to two home buttons | 5:00:00
| Friday | 7/1/2016 | 13:00 | 21:00 | 15:30 | 16:00 | Tested the website and found bugs. Help group fix bugs. Work on Recent History feature. | 7:30:00
4 | 8 | [6 empty] | 0:00:00
| Saturday | 7/2/2016 | [5 empty] | 0:00:00
| Sunday | 7/3/2016 | 15:00 | 22:30 | 19:00 | 20:00 | Worked on and finished recent history feature | 6:30:00
| Monday | 7/4/2016 | [5 empty] | 0:00:00
| Tuesday | 7/5/2016 | 15:00 | 21:00 | 16:00 | 16:30 | Worked on feature documents | 5:30:00
| Wednesday | 7/6/2016 | 14:00 | 20:00 | 15:00 | 15:30 | Created Controller, Module, Service, and View Page skeletons for admin panel, fixed buttons on main page, created new tasks for admin panel user story | 5:30:00
| Thusday | 7/7/2016 | 15:00 | 19:00 |  |  | Worked on Layout for Admin Panel View | 4:00:00
| Friday | 7/8/2016 | 13:30 | 19:30 | 15:00 | 16:00 | Worked on controller function for admin panel and modified ProfileAPI and AdminService | 5:00:00
| 9 | [6 empty] | 0:00:00
| Saturday | 7/9/2016 | [5 empty] | 0:00:00
| Sunday | 7/10/2016 | [5 empty] | 0:00:00
| Monday | 7/11/2016 | 9:00 | 15:00 | 12:00 | 12:30 | Fix bugs and work on user stories. | 5:30:00
| Tuesday | 7/12/2016 | 9:00 | 15:00 | 12:00 | 12:30 | Fix bugs and work on user stories. | 5:30:00
| Wednesday | 7/13/2016 | 9:00 | 15:00 | 12:00 | 12:30 | Fix bugs and work on user stories. | 5:30:00
| Thusday | 7/14/2016 | 9:00 | 15:00 | 12:00 | 12:30 | Fix bugs and work on user stories. | 5:30:00
| Friday | 7/15/2016 | 9:00 | 15:00 | 12:00 | 12:30 | Fix bugs and work on user stories. | 5:30:00
5 | 10 | [6 empty] | 0:00:00
| Saturday | 7/16/2016 | [5 empty] | 0:00:00
| Sunday | 7/17/2016 | [5 empty] | 0:00:00
| Monday | 7/18/2016 | 9:00 | 15:00 | 12:00 | 12:30 | Prepare for fifth sprint. | 5:30:00
| Tuesday | 7/19/2016 | 9:00 | 15:00 | 12:00 | 12:30 | Fix bugs and work on user stories. | 5:30:00
| Wednesday | 7/20/2016 | 9:00 | 15:00 | 12:00 | 12:30 | Fix bugs and work on user stories. | 5:30:00
| Thusday | 7/21/2016 | 9:00 | 15:00 | 12:00 | 12:30 | Fix bugs and work on user stories. | 5:30:00
| Friday | 7/22/2016 | 9:00 | 15:00 | 12:00 | 12:30 | Fix bugs and work on user stories. | 5:30:00
| 11 | [6 empty] | 0:00:00
| Saturday | 7/23/2016 | [5 empty] | 0:00:00
| Sunday | 7/24/2016 | [5 empty] | 0:00:00
| Monday | 7/25/2016 | 9:00 | 15:00 | 12:00 | 12:30 | Fix bugs and work on user stories. | 5:30:00
| Tuesday | 7/26/2016 | 9:00 | 15:00 | 12:00 | 12:30 | Fix bugs and work on user stories. | 5:30:00
| Wednesday | 7/27/2016 | 9:00 | 15:00 | 12:00 | 12:30 | Fix bugs and work on user stories. | 5:30:00
| Thusday | 7/28/2016 | 9:00 | 15:00 | 12:00 | 12:30 | Fix bugs and work on user stories. | 5:30:00
| Friday | 7/29/2016 | 9:00 | 15:00 | 12:00 | 12:30 | Fix bugs and work on user stories. | 5:30:00
6 | 12 | [6 empty] | 0:00:00
| Saturday | 7/30/2016 | [5 empty] | 0:00:00
| Sunday | 7/31/2016 | [5 empty] | 0:00:00
| Monday | 8/1/2016 | 9:00 | 15:00 | 12:00 | 12:30 | Work on poster. | 5:30:00
| Tuesday | 8/2/2016 | 9:00 | 15:00 | 12:00 | 12:30 | Work on videos. | 5:30:00
| Wednesday | 8/3/2016 | 9:00 | 15:00 | 12:00 | 12:30 | Work on videos. | 5:30:00
| Thusday | 8/4/2016 | 9:00 | 15:00 | 12:00 | 12:30 | Work on final deliverables. | 5:30:00
| Friday | 8/5/2016 | 9:00 | 15:00 | 12:00 | 12:30 | Present and fill out survey. | 5:30:00

## Johnny
Sprint # | Day of Week | Date | Check In | Check Out | Lunch In | Lunch Out | Short description of your work | Daily Hours | Weekly Hours | Overtime Hours | Approval
0 | 1
| Saturday | 2016-05-14 | [5 empty] | 0:00:00
| Sunday | 5/15/2016 | [5 empty] | 0:00:00
| Monday | 5/16/2016 | 19:45 | 21:45 |  |  | Learn about senior project | 2:00:00
| Tuesday | 5/17/2016 | 13:00 | 18:00 |  |  | Watch Videos | 5:00:00
| Wednesday | 5/18/2016 | 13:00 | 22:00 | 14:30 | 16:30 | Learn Angular JS | 7:00:00
| Thusday | 5/19/2016 | 15:00 | 20:00 |  |  | Learn Node JS, Express, and MongoDB | 5:00:00
| Friday | 5/20/2016 | 13:00 | 19:00 |  |  | Learn Git and setup MEAN stack | 6:00:00
1 | 2 | [6 empty] | 0:00:00
| Saturday | 5/21/2016 | [5 empty] | 0:00:00
| Sunday | 5/22/2016 | [5 empty] | 0:00:00
| Monday | 5/23/2016 | 20:30 | 23:00 |  |  | Make first commit of old code in GIT. | 2:30:00
| Tuesday | 5/24/2016 | 13:00 | 20:30 | 14:00 | 17:30 | Setup mingle account. | 4:00:00
| Wednesday | 5/25/2016 | 17:30 | 22:30 |  |  | Make feasibility report and make user storys for first sprint. | 5:00:00
| Thusday | 5/26/2016 | 12:30 | 23:00 | 19:30 | 22:30 | Met with Mohsen, discussed Google API and approach to implement. Synced branches and split user stories | 7:30:00
| Friday | 5/27/2016 | 19:00 | 1:00 |  |  | Reviewed Mohsens critique, setup robomongo, did research for user story. have story tasks but could not apply to mingle yet | -18:00:00
| 3 | [6 empty] | 0:00:00
| Saturday | 5/28/2016 | [5 empty] | 0:00:00
| Sunday | 5/29/2016 | [5 empty] | 0:00:00
| Monday | 5/30/2016 | [5 empty] | 0:00:00
| Tuesday | 5/31/2016 | 12:30 | 19:30 | 16:00 | 17:00 | Encountered issue affecting user story. COuld not test properly until fixed project appearance issue. Me, vlad and danny worked on solution. | 6:00:00
| Wednesday | 6/1/2016 | 19:00 | 0:00 |  |  | Tested user story #954. Began documentation. | -19:00:00
| Thusday | 6/2/2016 | 17:00 | 23:30 | 20:30 | 22:00 | Continued progress on user story #954 and documentation | 5:00:00
| Friday | 6/3/2016 | 17:00 | 18:00 |  |  |  | 1:00:00
2 | 4 | [6 empty] | 0:00:00
| Saturday | 6/4/2016 | 12:00 | 18:00 |  |  | Contiued research for fix for user story #954 | 6:00:00
| Sunday | 6/5/2016 | 12:00 | 15:00 |  |  | Worked with Daniel to fix story #954, issue was addressed. Updated document | 3:00:00
| Monday | 6/6/2016 | 18:00 | 22:00 |  |  | Met with Mohsen for sprint planning meeting. Created new stories. Met with team on approach for stories. | 4:00:00
| Tuesday | 6/7/2016 | 15:00 | 20:30 |  |  | refined user stories, looked for icon licensing issues, daily scrum with Mohsen | 5:30:00
| Wednesday | 6/8/2016 | 18:00 | 22:00 |  |  | Redesigned some icons i've found, asked teammates for opinions, reviewed button adding story | 4:00:00
| Thusday | 6/9/2016 | [5 empty] | 0:00:00
| Friday | 6/10/2016 | 20:30 | 0:00 |  |  | Added icons to the site, met with Mohsen for daily scrum, adjusted header height, added new user story | -20:30:00
| 5 | [6 empty] | 0:00:00
| Saturday | 6/11/2016 | [5 empty] | 0:00:00
| Sunday | 6/12/2016 | 17:00 | 20:00 |  |  | Refined user icons, added hover over text, started on story #1008, did document for story #972 | 3:00:00
| Monday | 6/13/2016 | 17:00 | 22:00 |  |  | Finished #1008, daily scrum with mohsen, created new user story | 5:00:00
| Tuesday | 6/14/2016 | 17:00 | 22:00 |  |  | Working on user story #1011, asked mohsen for story review, created related tasks | 5:00:00
| Wednesday | 6/15/2016 | 17:00 | 22:00 |  |  |  | 5:00:00
| Thusday | 6/16/2016 | 17:00 | 23:30 | 19:30 | 21:00 | Fixed git integration branch issue most of the day | 5:00:00
| Friday | 6/17/2016 | 17:00 | 22:00 |  |  |  | 5:00:00
3 | 6 | [6 empty] | 0:00:00
| Saturday | 6/18/2016 | [5 empty] | 0:00:00
| Sunday | 6/19/2016 | 9:00 | 14:30 |  |  | Finished testing main features on live site | 5:30:00
| Monday | 6/20/2016 | 17:00 | 22:00 |  |  | Went over bugs, met with mohsen, finished feature documents | 5:00:00
| Tuesday | 6/21/2016 | 16:00 | 21:00 |  |  | Had sprint planning meeting, worked with team to fix exception bug crashing server, created new stories | 5:00:00
| Wednesday | 6/22/2016 |  |  |  |  | Was not able to work, personal issue prevented me | 0:00:00
| Thusday | 6/23/2016 | 16:00 | 21:30 |  |  | Created related tasks, researched script for pop-ups | 5:30:00
| Friday | 6/24/2016 | 16:00 | 22:00 |  |  | Began work on teams page on local server | 6:00:00
| 7 | [6 empty] | 0:00:00
| Saturday | 6/25/2016 | [5 empty] | 0:00:00
| Sunday | 6/26/2016 | 17:30 | 23:00 |  |  | Worked on presentation slides with teammates | 5:30:00
| Monday | 6/27/2016 | 12:00 | 18:00 |  |  | Built presentation slides and practiced for presentation with team | 6:00:00
| Tuesday | 6/28/2016 | 17:30 | 22:00 |  |  | Got notifications to become pop-ups. Working on refresh after confirm. Students now show on teams page. | 4:30:00
| Wednesday | 6/29/2016 | 18:00 | 23:00 |  |  | Demo'd features with Mohsen, finished pop-up story, pushed minor updates to teams page UI | 5:00:00
| Thusday | 6/30/2016 | 16:00 | 21:00 |  |  | Added dynamic buttons to teams page, message buttons and fix HTML bug | 5:00:00
| Friday | 7/1/2016 | 18:00 | 23:00 |  |  | Added delete account feature and functionality, worked with danny to add default project images. Did user documents | 5:00:00
4 | 8 | [6 empty] | 0:00:00
| Saturday | 7/2/2016 | [5 empty] | 0:00:00
| Sunday | 7/3/2016 | 18:00 | 23:00 |  |  | Built presentation slides | 5:00:00
| Monday | 7/4/2016 | 18:00 | 23:00 |  |  | Presented | 5:00:00
| Tuesday | 7/5/2016 | 15:00 | 21:00 |  |  | Had sprint retrospective, picked new user stories | 6:00:00
| Wednesday | 7/6/2016 | 18:00 | 23:00 |  |  | Refined user stories, added related tasks, built tech support form and emails | 5:00:00
| Thusday | 7/7/2016 | 18:00 | 23:00 |  |  | Worked on Teams page UI | 5:00:00
| Friday | 7/8/2016 | 18:00 | 23:00 |  |  | Worked on implementing video and gallery function | 5:00:00
| 9 | [6 empty] | 0:00:00
| Saturday | 7/9/2016 | [5 empty] | 0:00:00
| Sunday | 7/10/2016 | [5 empty] | 0:00:00
| Monday | 7/11/2016 | 9:00 | 15:00 | 12:00 | 12:30 | Fix bugs and work on user stories. | 5:30:00
| Tuesday | 7/12/2016 | 9:00 | 15:00 | 12:00 | 12:30 | Fix bugs and work on user stories. | 5:30:00
| Wednesday | 7/13/2016 | 9:00 | 15:00 | 12:00 | 12:30 | Fix bugs and work on user stories. | 5:30:00
| Thusday | 7/14/2016 | 9:00 | 15:00 | 12:00 | 12:30 | Fix bugs and work on user stories. | 5:30:00
| Friday | 7/15/2016 | 9:00 | 15:00 | 12:00 | 12:30 | Fix bugs and work on user stories. | 5:30:00
5 | 10 | [6 empty] | 0:00:00
| Saturday | 7/16/2016 | [5 empty] | 0:00:00
| Sunday | 7/17/2016 | [5 empty] | 0:00:00
| Monday | 7/18/2016 | 9:00 | 15:00 | 12:00 | 12:30 | Prepare for fifth sprint. | 5:30:00
| Tuesday | 7/19/2016 | 9:00 | 15:00 | 12:00 | 12:30 | Fix bugs and work on user stories. | 5:30:00
| Wednesday | 7/20/2016 | 9:00 | 15:00 | 12:00 | 12:30 | Fix bugs and work on user stories. | 5:30:00
| Thusday | 7/21/2016 | 9:00 | 15:00 | 12:00 | 12:30 | Fix bugs and work on user stories. | 5:30:00
| Friday | 7/22/2016 | 9:00 | 15:00 | 12:00 | 12:30 | Fix bugs and work on user stories. | 5:30:00
| 11 | [6 empty] | 0:00:00
| Saturday | 7/23/2016 | [5 empty] | 0:00:00
| Sunday | 7/24/2016 | [5 empty] | 0:00:00
| Monday | 7/25/2016 | 9:00 | 15:00 | 12:00 | 12:30 | Fix bugs and work on user stories. | 5:30:00
| Tuesday | 7/26/2016 | 9:00 | 15:00 | 12:00 | 12:30 | Fix bugs and work on user stories. | 5:30:00
| Wednesday | 7/27/2016 | 9:00 | 15:00 | 12:00 | 12:30 | Fix bugs and work on user stories. | 5:30:00
| Thusday | 7/28/2016 | 9:00 | 15:00 | 12:00 | 12:30 | Fix bugs and work on user stories. | 5:30:00
| Friday | 7/29/2016 | 9:00 | 15:00 | 12:00 | 12:30 | Fix bugs and work on user stories. | 5:30:00
6 | 12 | [6 empty] | 0:00:00
| Saturday | 7/30/2016 | [5 empty] | 0:00:00
| Sunday | 7/31/2016 | [5 empty] | 0:00:00
| Monday | 8/1/2016 | 9:00 | 15:00 | 12:00 | 12:30 | Work on poster. | 5:30:00
| Tuesday | 8/2/2016 | 9:00 | 15:00 | 12:00 | 12:30 | Work on videos. | 5:30:00
| Wednesday | 8/3/2016 | 9:00 | 15:00 | 12:00 | 12:30 | Work on videos. | 5:30:00
| Thusday | 8/4/2016 | 9:00 | 15:00 | 12:00 | 12:30 | Work on final deliverables. | 5:30:00
| Friday | 8/5/2016 | 9:00 | 15:00 | 12:00 | 12:30 | Present and fill out survey. | 5:30:00